Government of Nepal

Ministry of Physical Planning and Works

DEPARTMENT OF ROADS

ROAD NETWORK DEVELOPMENT PROJECT

Asian Development Bank Loan No. 1876 – NEP(SF)

# Resettlement Monitoring Quarterly Report

# August 2007 – December 2007

- Progress towards Completion of Resettlement Activities on

Each Road Section to 10 December 2007

Resettlement progress is summarised in the following Table 1.

Table 1: Summary of Land Acquisition and Resettlement Impact

| SN | Description | DC | PP | DG | HB | BM | BBUB | MK | Total Project |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Total Impact |  |  |  |  |  |  |  |  |
| 1.1 | Affected Households (HH) | 113 | 81 | 227 | 30 | 8 | 394 | 519 | 1,372 |
| 1.2 | Affected person (APs) | 842 | 639 | 1,430 | 183 | 48 | 2,655 | 3,010 | 8,807 |
| 1.3 | Affected HHs losing<10% assets | 113 | 81 | 224 | 182 | 8 | 376 | 0 | 984 |
| 1.4 | Affected HHs losing>10% assets | 0 | 0 | 3 | 1 | 0 | 18 | 0 | 22 |
| 2 | Loss of Land |  |  |  |  |  |  |  |  |
| 2.1 | HHs losing land | 0 | 0 | 111 | 27 | 7 | 209 | 292 | 646 |
| 2.2 | Total amount of affected land (NRs) | 0 | 0 | 872,262 | 177,653 | 139,979 | 1,582,652 | 10,126,403 | 12,898,949 |
| 2.3 | Total Land acquisition (ha) | 0 | 0 | 0.59 | 0.15 | 0.19 | 1.4 | 10.3 | 12.63 |
| 2.4 | Land acquisition under RNDP (ha) | 0 | 0 | 0.59 | 0.15 | 0.19 | 1.4 | 1.1 | 3.43 |
| 2.5 | Compensation paid for new land (RNDP) | 0 | 0 | 872,262 | 177,653 | 139,979 | 1,361,750 | 814,173 | 3,365,817 |
|  | Land acquisition Arun Access (ha) |  |  |  |  |  |  | 3.7 | 3.7 |
| 2.6 | Compensation paid for Arun Access |  |  |  |  |  |  | 3,887,824 | 3,887,824 |
|  | DoR opened road/Existing road (ha) |  |  |  |  |  |  | 5.5 | 5.5 |
|  | Compensation paid for existing road |  |  |  |  |  |  | 2,279,761 | 2,279,761 |
|  | Is there an existing road? | Yes | Yes | Yes | Yes | Yes | Yes | Partial |  |
| 2.7 | RoW declared through Gazette? | Yes | Yes | No | No | No | Partial | No |  |
| 3 | Loss of House and Structure |  |  |  |  |  |  |  |  |
| 3.1 | Total HHs losing structures | 9 | 3 | 3 | 3 | 0 | 33 | 16 | 67 |
| 3.2 | Total affected structures | 10 | 3 | 4 | 3 | 0 | 40 | 24 | 84 |
| 3.3 | Households losing structure with private land | No | 0 | None | 2 | 0 | 14 | 11 |  |
| 3.4 | Households losing structure without land | 9 | 3 | 3 | 1 | 0 | 19 | 5 | 40 |
| 3.5 | Compensation amount for affected structure (NRs) | 607,315 | 26,000 | 137,000 | 228,630 | 0 | 1,401,255 | 989,516 | 3,389,716 |
| 3.6 | Compensation paid (%) | 100% | 100% | 100% | 100% | 0 | 100% | 100% |  |
| 4 | Loss of trees and crops |  |  |  |  |  |  |  |  |
| 4.1 | Total affected trees/crops | 652 | 737 | 438 | 0 | 10 | 2969 | 7984 | 12790 |
| 4.2 | Compensation amount for affected trees/crops (NRs) | 126,892 | 112,310 | 87,251 | 0 | 7,291 | 298,261 | 1,566,873 | 2,198,878 |
| 4.3 | Compensation paid (%) | 100% | 100% | 100% | 0 | 91% | 100% | 93% |  |
| 4.4 | Households losing tress with land | No | No | 3 | 0 | 5% absentee | 79 | 18 |  |
| 4.5 | Households losing trees without land(existing RoW/Arun Access) | 113 | 78 | 81 | 0 | 1 | 119 | 199 | 591 |
| 5 | Community Forestry |  |  |  |  |  |  |  |  |
| 5.1 | Community trees acquired | 1,132 | 0 | No | 0 | 0 | 0 | 4,186 |  |
| 5.2 | No of affected forest users group | 11 | 0 | No | 0 | 0 | 0 | 7 |  |
|  | Compensation paid (NRs) | 220,745 | 0 | No | 0 | 0 | 0 | 415,649 |  |
| 5.3 | Compensation paid (%) | 100% | 0 | No | 0 | 0 | 0 | 100% |  |
| 6 | Non title holders and others APS |  |  |  |  |  |  |  |  |
| 6.1 | Squatters affected (HH) | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  |
| 6.2 | Sharecropper/Tenants (HH) | 0 | 0 | 32 | 2 | 0 | 46 | 0 |  |
| 6.2 | Wage labours (HH) | 0 | 0 | No |  |  | 1 | 21 |  |

2.   	Mudhe - Khandbari Feeder Road

2.1		Mudhe to Sabha Khola Road Section

Of the 337 land plots to be acquired, 11 are government land and require no compensation, 218 further plots have been compensated and 108 parcels remain to be compensated.  Of the 108 parcels, the owners of 49 parcels are absentee, 20 are subject to High Court stay of Action and cannot be paid as yet.  This leaves 39 parcels remaining. Payment for these parcels (7% of the total land compensation) awaits the redeployment of a Government Officer to Chainpur.  The money is already transferred to the CDO account and can be dispensed as soon as the Officer is in place and people travel to collect the money.

NRs 106,368 remains to be paid for trees, all of whose owners are absent.  The money is lodged with the CDO and can be paid when the owners are available to collect.  All community forestry payments have been completed.

The (two) Poverty Intervention Component NGOs have been deployed to the road and are have been directed to assist AP households to obtain unskilled labour employment with the contractors and then to assist in finding other local labour, especially women.

- No action has been taken to instigate the Local Consultative Forum (LCF) programme in each VDC.

ACTION:                       Project Manager/ NGOs

- Social Compliance monitoring has been undertaken during November/ December 2007 and a draft report written.  Compliance on MK is better than in the previous year on the other RNDP roads.  Most MK contractors have had other RNDP experience and this may explain some of the observed improvement.  Employment of local people as unskilled labour and employment of women is particularly poor, although health and safety aspects are a little improved.

ACTION: 	       REs to continue checking

- Two NGOs appointed and mobilised to MK have budgets sufficient to provide savings and credit groups only; no money has been allocated for life-skills, income generation training or small scale infrastructure development schemes and none it is understood that funding from DoR is unlikely.  The DfID Enhancing and Protecting Mechanisms, previously part of the RAP approach to the road construction for the MK road section, have been lost.

ACTION:              PD to consider authorising

finance for additional PIC works

2.2		Sabha Khola to Khandbari

No action has been taken on this section in this period as it has been excluded from the present Project.

3		Hile-Basantapur-Mudhe

Construction of Contracts HB-1 and HB-2 is complete. Contracts HB-3 is approximately 56% complete, Contract HB-4 40% and Contract BM 22%.

All payments for all compensation on these road sections are now complete.

The NGO appointed to the HB and BM road sections has completed the tasks contracted, with 25 (out of 30) affected families having joined the savings and credit schemes. This programme has been very successful with loan repayment running at 100%. Many borrowers have used the loan for skills training.  A separate report on the current situation of the Poverty Intervention Component has been drafted and will be submitted shortly.

ACTION:                   DoR to forward to ADB

4		Biratnagar- Rangeli- Bardanga, Urlabari-Bardanga (BBUB)

This Contract is nearing completion.

80 plots still remain to be compensated for; all of these refer to plots with absentee owners or where mortgages apply.  Resettlement payments are, therefore, complete.

ACTION:                 No Action

5		Pouwa-Phidim (PP)

Construction work is completed.

No resettlement compensation payments issues are outstanding on this road section.

The NGO for this road section is deployed under the separate (TA4760) funding.  There is no RNDP social development input to monitor this activity.

ACTION:                 No Action

6	Damak-Gauriganj (DG)

Construction work is completed.

22 plots which remain uncompensated as their owners are absent.

The NGO for this road section is deployed under the separate (TA4760) funding.  There is no RNDP social development input to monitor this activity.

ACTION:                   No Action

7	Dolalghat-Chautara

Construction work is completed.

No progress has been made towards resolution of the community’s refusal to transfer the title deeds of the land under the road despite considerable input from a number of government agencies.  As a consequence land tax will still be levied on the land under the road and the deeds have not been transferred to DoR.

Payments for absentee landowners’ crops and trees have been notified, the money deposited with the CDO and responsibility for its correct disbursement has been transferred to the CDO and is no longer a DoR responsibility.

The NGO (Sahara) for this road section has finished its input without a formal monitoring visit.  75 of the 200 savings and credit scheme members came from affected families.  The poverty intervention component NGO programme was truncated by DoR in order to finish works by the end of RNDP on this road.  A separate Poverty Intervention Component Monitoring Report has been written on this subject.

ACTION:                         No Action

8	Main Outstanding Resettlement Issues

The main outstanding resettlement issues are:

- confirmation of title transfer for new and existing land acquisition on MK, BBUB and DC.

- completion of the last remaining acquisitions for MK.

- LCF meetings - it is strongly recommended that these meetings should be held on Mudhe-Khandbari Road section and the proceedings of such meetings properly recorded for future reference.

### 9  	Poverty Intervention Component on Mudhe-Khandbari Road Section

A monitoring visit has been made this quarter to the two NGOs deployed to this section.  The NGOs are in the process of mobilising and will start visiting APs and the Contractors in December 2007.  The social mobilisers have been instructed to prioritise contacting AP families and introducing interested family members to the Contractors for preferential employment along each section.  After this, the NGOs will focus on savings and credit group formation.  Unfortunately, the amounts allocated to the NGOs and the duration of their inputs is insufficient to make any substantial differences to poverty incidence and income generation.  However, both NGOs are able to link the RNDP savings groups to programmes of other donors to assist in reducing the impact of this shortfall in the RNDP input.

Under the original labour-intensive road building group approach, a sum of Rs 1,000,000 was to be allocated from DfID for support to income generation/poverty reduction and life-skills training. With the change to contractor based construction in mid 2006, this allocation was lost and it appears that it cannot be replaced from the ADB loan funds or by DoR budget provision.

ACTION: 		PIC review report to be agreed and distributed

### 10    Poverty Intervention Component on Dolalghat-Chautara, Hile-Basantapur and Basantpur - Mudhe Road Sections

A monitoring visit has been made to these road sections this quarter and a separate report prepared.  The main conclusions are:

- The delays in awarding the NGO contracts and in mobilisation, until after the construction contracts were well underway, effectively removed the link between local unskilled labourers and the NGOs but resettlement Affected Families have been included.

- The local labour employment on these roads has been negligible, partly because local people are not willing to work as unskilled labour (some are working as supervisors) and because the Contractors prefer captive labour to local incidentally available workers.

- 10 Savings and Credit Groups with 200-215 members have been created and are working well.  Both NGOs are continuing to support these groups using funding available from other donor programmes.

- DoR needs to institutionalise the findings of the TA in order to be able to deploy NGOs more effectively and in a timely fashion.

ACTION: 		Accept and distribute Monitoring Report.

### 11 	Poverty Intervention Component on BBUB, DG and PP Road Sections

It is considered that a monitoring input by the RNDP Consultants into this programme would be highly beneficial to compare experiences with the TA team working on these road sections.  The TA team has been approached for sight of any monitoring reports and it is intended that these will be evaluated and reported upon in the next RNDP Quarterly Monitoring Report.

ACTION: 		      ADB/ NRM

### 12	 Monitoring Resettlement Impact

The Monitoring Survey of Resettlement Impact has been undertaken and is awaiting some final data, after which the report will be presented to DoR, by mid January 2008.

ACTION:           SD/R Specialist

### 13	  Analysis and Reporting of the Socio-Economic Baseline Surveys

The analysis has been undertaken and is currently being finalised by the International Social Development/Resettlement Specialist. This work will be completed as soon as possible.  Some clarifications of certain data tables have been requested from the data analyst and, once received,  will be incorporated into the reports for each road and the reports issued.

ACTION:            SD/R Specialist

### 14	  Monitoring Social Compliance

A social compliance audit for Mudhe-Khandbari Road section was undertaken in November/December 2007.  The draft report is complete and will be available shortly for agreement and dissemination.

ACTION:          SD/R Specialist

/Team Leader