Annex II-3: Monitoring Outputs and Activities wrt Yearly Targets - Table 2&3–Road and Transport Sector

| Major Programs wrt Sectoral Outcomes | Outcome and Output Indicators | Agencies/ Dept./PEs/ Divisions | Sub- programs / Projects |  |  | Baseline June 2010 | Business Plan – Yearly Output Targets & Progress |  |  |  | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Road Section |  | Tot.-km |  | Target FY 2067/68 (2010-11) | Progress as of July 2011 | Target FY 2068/69 (2011/12) | Target FY 2069/70 (2012/13) |  |  |
| - Programs for Roads Connecting District Headquarters and its upgrading. Outcome: Access to all the district headquarters of Nepal facilitated. | - No. of DHQs connected to road network | Nepal Army |  | 1.1 New Road Construction |  | 176 |  |  |  |  |  |  |
|  |  |  |  | - Nagma-Gamgadhi | 91 | 58 | Track - 28 km |  | Track- remaining 5 km Continue with C&GI | Continue with C&GI |  |  |
|  |  |  |  | - Jajarkot-Dunai(Dolpa) | 144 | 23 | Track – 22 km |  | Track – 20 km | Track – 20 km and remaining 46 km in next years |  |  |
|  |  |  |  | - Besisahar Chame | 65 | 60 | Track - remaining 5 km Continue with C&GI. |  | Continue with C&GI. | Continue with C&GI. |  |  |
|  |  | DOR |  | - Karnali: Hilsa – Simikot under North South Lok Marg | 88 | 35 | Track – 0 km |  | Track – 15 km | Track – 14 km: remaining 24 km in next years |  |  |
|  | - No. of DHQs with year round road accessibility 8+5+4+5= 22 - Reduction in the time to travel up to the DHQ. - Additonal poluation within the reach of 2 to 4 hours walking to the road access - No. of new settlements connected with road. | DOR |  | 1.2 Road Upgradation for DHQs |  |  |  |  |  |  |  |  |
|  |  |  |  | - Road Improvement Project (RIP) - (total 17 nos.) including 8 road sections connecting DHQ including Salyan, Dailekh, Bajura, Achham, Terhathum, Khotang, Pyuthan & Myagdi. | 484 | 204 | Complete BT –Strngthg. of Chapur-Gaur 25 km Continue with BT upgrading works for 249 km (Also refer 2.1 below) |  | Continue with BT upgrading works for 79 km (Also refer 2.1 below) | Continue with BT upgrading works for 18 km, |  |  |
|  |  |  |  | - Road Sector Development Project I & II -(total) including 5 roads connecting DHQs including Darchula and Bajhang, Jumla, Jajarkot & Rukum | 512 |  | Continue with BT upgrading for 28 km. Periodic Maintenance – 165 km |  | Continue with BT upgrading for 122 km. Periodic Maintenance – 70 km | Continue with BT upgrading for 275 km. Periodic Maintenance – 70 km |  |  |
|  |  |  |  | - Sub-regional Transport Enhacement Project including 4 roads connecting DHQs of Okhaldhunga, Solukhumbu, Sankhuwasabha, Bhairahwa. | 184.5 |  | Design, Tendering, Contract award for 4 roads projects - |  | BT upgrading for 95 km. | BT upgrading for 89.5 km. |  |  |
|  |  |  |  | - 5 roads connecting DHQs under Road Connectivity Project I + Sunkoshi Bridge - DHQs included of Rasuwa, Ramechhap, Dhanusha, Taplejung,& Kapilvastu, | 317 |  | Continue with BT upgrading for 240 km. Continue with Sunkoshi bridge |  | Continue with BT upgrading for 42 km. Continue with Sunkoshi bridge | Continue with Sunkoshi bridge |  |  |
| - Programs for improving accessibility in dense settlements of terai and hills as well as administrative, commercial, tourism and industrial centers. Outcome: Access to terai and hills cluster settlements and administrative, commercial, tourism and industrial centre to be convenient. | - Additonal population within the reach of 2 to 4 hours walking to the road access - No. of new settlements connected with road. - Increase in road intensity. - Reduction in travel time for east west travel in the mid hill areas - Reduction in travel time for travel between Kathmandu and terai. - Increase in access to social services such as education, health. |  |  | 2.1 North-south trade and transit roads. |  |  |  |  |  |  |  |  |
|  |  | Nepal Army |  | - Kathmandu-Tarai-Madhesh Fast Track | 77 | 21 | Track -remaining – 55 km |  | Continue with curve & grade improvement, repair & maintenance and structure works including Bailey Bridge |  |  |  |
|  |  |  |  | - Banglung Beni Jomsom | 97 |  | Continue with C&GI., R & M, structure works |  | Continue with C&GI., R & M, structure works | Continue with C&GI., R & M, structure works |  |  |
|  |  | DOR DOR |  | - Kathmandu-Tarai-Madhesh Fast Track | 77 |  | Continue with Land acquisition and other activities |  | Continue with Land acquisition and other activities | Continue with Land acquisition and other activities |  |  |
|  |  |  |  | - Banglung Beni Jomsom | 97 | 97 | Continue with BT works - 2 km, GR works – 0.3 km |  | Continue with BT works - 3 km, GR works – 17 km | Continue with BT works - 4 km, GR works – 18 km |  |  |
|  |  |  |  | - Syaphrubesi Rasuwagadhi | 16 | 16 | Continue with GR works – 9 km, and Bridge -9 nos. |  | Continue with GR works – 7 km, and Bridge -9 nos. | Continue with Bridge -9 nos. |  |  |
|  |  |  |  | - B P Koirala Lokmarg (Banepa-Sindhuli-Bardibas) | 160 | 123 | Continue with BT works - 18 km Drain & structures in 4 km stretch of third section. |  | Continue with BT works - 10 km | Continue with BT works - 15 km |  |  |
|  |  |  |  | - Mahakali Lokjmarg (Darchula-Tinker Section) | 90 | 3 | Continue with Track – 25 km Complete bridge design and EIA and award contract. |  | Continue with opening track – 32 km | Continue with opening track – 30 km |  |  |
|  |  |  |  | - 4 NS trade & Transit Roads under RIP (6 lane widening of 4 road sections namely (i) Rani Itahari-Dharan 50km (ii) Birgunj Pathlaiya 28km, (iii) Beliya-Butwal 24 km, (iv) Suryabinayak-Dhulikhel 16km. | 118 |  | Survey and DPR Preparation, Tendering & Contract Award plus Construction of Embankments. |  | Complete widening & strengthening of 4 roads - 20 km | Complete widening & strengthening of 4 roads - 45 km |  |  |
|  |  |  |  | - Sankhu Melamchi & Tokha-Chhahare under Road Improvement Project(RIP) (included under RIP in 1.2 as above) | 58 |  | Continue with BT - 28 km – |  | Continue with BT - remaining 21 km |  |  |  |
|  |  |  |  | - 7 North-South Roads along Karnali, Kaligandaki & Koshi | 931 | 491 | Continue with Track opening – 70 km and GR works – 5 km. Prepare DPR |  | Continue with track opening – 100 km and GR works – 30 km. | Continue with track – 110 km and GR works – 90 km. Start BT works – 5 km |  |  |
|  |  |  |  | 2.2 Mid Hill Road Development Program |  |  |  |  |  |  |  |  |
|  |  | Nepal Army |  | - Musikot-Burtibang | 145 | 28 | Continue with track opening – 8 km |  | Continue with track opening – 6 km | Continue with track opening – 4 km |  |  |
|  |  | DOR |  | - Puspalal Lokmarg (Mid Hill Lokmarg) | 810 | 584 | Continue with track opening – 226 km and GR works – 15 km |  | Continue with track opening – 15 km and GR works – 140 km | Continue with track opening – 20 km and GR works – 150 km |  |  |
|  |  |  |  | 2.3 Upgradation of Postal (Hulaki) and other roads of strategic importance |  |  |  |  |  |  |  |  |
|  |  |  |  | - Postal Roads including Bridges (Phase I only, Total three phase 1500km) | 640 |  | Continue with BT works – 33 km Continue with Bridges – 5 no. |  | Continue with BT works – 640 km Continue with Bridges – 16 no. | Continue with BT works – 430 km Continue with Bridges – 18 no. |  |  |
|  |  |  |  | - Rapti Lokmarg (Sallyan-Musikot Blacktop) | 86 |  | Continue with GR works – 30 km |  |  |  |  |  |
|  |  |  |  | - Kanti Lokpath | 93 |  | Continue with BT works – 1 km and GR works – 12 km |  | Continue with BT works – 1.5 km and GR works – 16 km | Continue with BT works – 2 km and GR works – 16 km |  |  |
|  |  |  |  | - Naradmuni Thulung Marg (Hile-Leguwaghat-Bhojpur) | 93 |  | Continue with GR works – 15 km |  | Continue with GR works – 12 km | Continue with GR works – 11 km |  |  |
|  |  |  |  | - Ganeshman Singh Marg(Thankot-Chitlang) | 20 |  | Continue with BT works – 1 km |  | Continue with BT works – 4 km | Continue with BT works – 2 km |  |  |
|  |  |  |  | - Byas Marg | 31 |  | Continue with BT works – 6 km |  | Continue with BT works – 5 km | Continue with BT works – 5 km |  |  |
|  |  |  |  | - Dharan Chatara Gaighat Katari Sindhuli Bazar-Hetauda | 325 |  | Continue with BT works – 8 km and GR works – 8 km |  | Continue with BT works – 13 km and GR works – 13 km | Continue with BT works – 17 km and GR works – 17 km |  |  |
|  |  |  |  | - 11 Kilo Chhepetar Bhaluswara Warpak | 53 |  | Continue with BT works – 3.2 km and GR works – 5 km |  | Continue with BT works – 4 km and GR works – 6 km | Continue with BT works – 4 km and GR works – 6 km |  |  |
|  |  |  |  | - Fikkal Shree Antu Danda Road | 14 |  | Continue with BT works – 3.5 km |  | Continue with BT works – 4 km | Continue with BT works – 4.5 km |  |  |
|  |  |  |  | - Dakchinkali Chaimale Sisneri Kulekhani | 19 |  | Continue with BT works – 8 km |  | Continue with BT works – 11 km |  |  |  |
|  |  |  |  | - Road Connectivity Project II (Pdirect.& Consultancy Services and road upgrading) | 300 |  | Selection of Consultant |  | Survey, Design and Contract Award | Commence BT works – 15 km |  |  |
|  |  |  |  | 2.4 New Road Construction and Extension |  |  |  |  |  |  |  |  |
|  |  |  |  | - Sagarmatha Lokmarg (Gaighat- Diktel Section) | 131 | 48 | Continue with track opening – 7 km, GR works –5 km and BT works –0.5 km |  | Continue with track opening – 15 km and GR works – 7 km | Continue with track opening – 25 km and GR works – 7 km |  |  |
|  |  |  |  | - Seti Lokmarg ( Tikapur-Lode-Chainpur-Taklakot) - Survey & EIA for 40 km to be done for each of three years | 285 | 22 | Continue with track opening – 9 km and GR works – 3 km |  | Continue with track opening – 15 km and GR works – 3 km | Continue with track opening – 19 km and GR works – 4 km |  |  |
|  |  |  |  | - Tourism Roads - 23 road sections for upgrading and new construction |  |  | Started this year 2067-68, Complete BT upgrading works - 10 km Start ER works –20 km |  | Continue with BT upgrading works - 10 km , ER works –5 km and GR works – 5 km | Continue with BT upgrading works - 15 km , ER works –5 km and GR works – 5 km |  |  |
|  |  |  |  | - Central Level (Various phase-wise roads) |  |  | Continue with track opening – 90 km, GR works – 20 km and BT works – 3 km |  | Continue with track opening – 90 km, GR works – 20 km and BT works – 3 km | Continue with track opening – 90 km, GR works – 20 km and BT works – 3 km |  |  |
|  |  |  |  | - Regional Level Roads (34 plus 40 Nos) | 0 |  | Continue with track Opening and ER roads – 70 km, GR works – 40 km |  | Continue with track Opening and ER roads – 70 km, GR works – 40 km and BT – 30 km | Continue with GR works – 70 km |  |  |
|  |  |  |  | - Gangate Labhdu Samudratar Galfu Bhanjyang | 63 | 35 | Continue with track opening – 5 km and BT works – 3 km |  | Continue with track opening – 6 km and BT works – 3 km | Continue with track opening – 8 km and BT works – 3 km |  |  |
|  |  |  |  | - Saljhundi Sandhikhark Dhorpatan Road | 128 | 62 | Continue with track opening – 14 km and GR works – 2 km |  | Continue with track opening – 30 km | Continue with track opening – 22 km and GR works – 5 km |  |  |
|  |  |  |  | - Chepang Marg (Bhandara-Lothar-Malekhu) | 60 | 50 | Continue with track opening – 10 km and GR works – 15 km |  | Continue with GR works – 28 km | Continue with GR works – 17 km |  |  |
|  |  |  |  | - Tanakpur Link Road | 14 | 14 | Continue with BT works – 6 km |  | Continue with BT works – 5 km | Continue with BT works – 3 km |  |  |
|  |  |  |  | - Sahid Marg (Tila Ghartigaon Thawang Rukumkot) - track to be opened upto MHH | 177 | 103 | Continue with track opening – 15 km |  | Continue with track opening – 15 km and GR works – 5 km | Continue with track opening – 20 km |  |  |
|  |  |  |  | - Benighat Aarughat Larkebhanjyang | 130 | 36 | Continue with track opening – 15 km |  | Continue with track opening – 6 km | Continue with track opening – 6 km |  |  |
|  |  |  |  | - Tallo Dhungeshore Satkhamba Dullu Pipalkot Dailekh | 33 | 29 | Continue with track opening – 3 km |  | Continue with track opening – 1 km and start GR works – 3 km | Continue with GR works – 5 km |  |  |
|  |  |  |  | - Gumi -Patihalna Chour (Surkhet) | 45 | 16 | Continue with track opening – 3 km |  | Continue with track opening – 3 km | Continue with track opening – 3 km |  |  |
|  |  |  |  | - Mirdi Kyakmi Bhimad | 59 | 52 | Continue with track opening – 3 km |  | Continue with track opening –2 km | Continue with track opening – 2 km |  |  |
|  |  |  |  | - Putalikhet-Karkineta-Kusma | 47 | 23 | Continue with track opening – 5 km |  | Continue with track opening – 10 km | Continue with track opening – 9 km |  |  |
|  |  |  |  | 2.5 Bridge Construction Program |  |  |  |  |  |  |  |  |
|  |  |  |  | - Bridge Construction along the Postal Roads |  |  |  | Refer section 2.3 above under Postal Roads |  |  |  |  |
|  |  |  |  | - Sunkoshi Bridge (Road Connectivity Project I) |  |  |  | Refer section 1.2 above under Road Connectivity Project |  |  |  |  |
|  |  |  |  | - Bridge Construction Program |  | Total 227 bridges under construction | 45 bridges to be completed this year |  | 50 bridges to be completed | 55 bridges to be completed |  |  |
|  |  |  |  | - Koshi Bridge (Chatara) (Flood Damaged Reconstruction Project) |  |  | Bridge construction at Chatra to continue |  | Bridge construction at Chatra to continue | Bridge construction at Chatra to continue |  |  |
| - Programs for expansion and improvement of transport facilities in the Kathmandu Valley and other urban centers of the country . | - Travel time within Kathamndu Valley to be reduced. - Redcution in air pollution. - Reduction in the number of road accidents. - Development of handicapped- friendly road structure. | DOR |  | 3.1 Urban Road Improvement Program - Kathmandu Bhaktapur Road Extension | 9 |  | Complete 1.7 km of remaining BT on main lanes |  | Complete BT works on service roads & other auxiliary works |  |  |  |
|  |  |  |  | - Kathmandu Valley Road Construction and Improvement |  |  | BT works – 55 km. on different road sections |  | BT works – 60 km. on different road sections | BT works – 65 km. on different road sections |  |  |
|  |  |  |  | - Kathmandu Valley Road Extension Project |  |  | BT works – 20 km. & widening strengthening 6 km |  | BT works – 35 km. & widening strengthening 10 km | BT works – 35 km. & widening strengthening 10 km |  |  |
|  |  |  |  | - Other Urban Roads |  |  | BT works – 10 km. & earthen works 10 km |  | BT works – 10 km. & Gravl 10 km | BT works – 10 km. & Grvl 15 km |  |  |
|  |  | MoPPW |  | - Kathmandu Sustainable Urban Transport Project |  |  | - Mobilization – selection of consultants |  | - Capacity building of PIUs, training and technical studies | - Construction of Bus stops, lay-bys, shelters and route improvement , CCTV | PIUs of MOEnv, DOR, KMC, DOTM & MTPD |  |
| - Programs for Feasibility studies and R&D on alternative transport (railways, waterways, ropeways etc.) system as well as on road safety. | - No. of studies for transport development based on alternative technology. - No. of feasibility studies done for road infrastructure developmetn. - No. of studies and reserach on road safety. | DOR |  | - Detailed Feasibility Studies of Roads and Bridges |  |  |  |  |  |  |  |  |
|  |  |  |  | - Planning, Program, M & E, Geo-environment studies etc. |  |  |  |  |  |  |  |  |
|  |  |  |  | - Transport Project Preparatory Facilitation (Feasibility & Design ADB) |  |  |  |  |  |  |  |  |
|  |  | MoPPW |  | - Water Way Project |  |  | - Complete feasibility study of Arun (45 km) and Tamaur (55 km) - Initiate feasibility study of Koshi, Gandaki and Bheri River Corridors –total 450km |  | - Removal of obstructiin Arun and Tamaur-. - Continue and complete feasibility study of Koshi, Gandaki and Bheri (450km) - Initiate feasibility study of other River Corridors | - Continue channeling & grading, constrct. of platform and stations in Arun and Tamaur-. - Removal of obstruction in Koshi, Gandaki & Bheri. - Continue and complete feasibility study of other river corridors. |  |  |
| - Program for Road Strengthening and Repair Maintenance | - Reduction in the operation cost of vehicle. - Reduction in travel time - Reduction in road accidents - Smoothness in the operation of transport service. - Strengthening and use of statistical base of DoR including local bodies. - Estab. and utilization of road asset protection system - Effectiveness of the maintenance fund under the Road Board. - Length and operation status of the road transferred to the local bodies. | DOR |  | - Karnali Lokmarg (Surkhet- Jumla) | 232 |  |  | Out of 232km, 126 km under RSDP for upgrading, rest between Kalikot-Jumla 106km track for curve & grade improvement |  |  |  |  |
|  |  |  |  | - Jaya Prithvi Bhadur Singh Marga, Khodpe bajhhang | 110 |  |  | Out of 65km track, 45 km under RSDP for upgrading and curve & grade improvement, repair & maintenance for rest of track. |  |  |  |  |
|  |  |  |  | - Damak Chisapani | 44 |  |  | 3 km GR in 2067-68 and 4km GR for next 2 years plus Grade & curve improvements, const. of Structures, repair & maintenance |  |  |  |  |
|  |  |  |  | - Bridge-culvert Conservation and Maintenance & Repair |  |  |  | 9 bridge in SRN to be repaired, historical data on SRN & FR bridges to be collected |  |  |  |  |
|  |  | MoPPW |  | - Flood Damaged Reconstruction Project |  |  | Repair & maintenance |  | Repair & maintenance | Repair & maintenance |  |  |
|  |  | RBN |  | - Road Boards Strategic Roads Periodic Maintenance | 1950 |  | Periodic Maintenance -400 km |  | Periodic Maintenance -700 km | Periodic Maintenance -800 km |  |  |
|  |  |  |  | - Road Boards Routine, Recurrent and Emergency Maintenance |  |  |  |  |  |  |  |  |
|  |  | Nepal Army |  | - Chhinchu Jajarkot |  |  |  | Grade & curve improvements, repair & maintenance for part of 45 km track that was opened under RSDP |  |  |  |  |
|  |  |  |  | - Devasthal-KanaiDanda-Chaurjhari |  |  |  | Grade & curve improvements, repair & maintenance for entire stretch |  |  |  |  |
| - Programs for Institutional Strengthening - including M&E and recurrent administrative budget expenses | - No. of projects completed on time. - No. of trained human power - Plan formulation and implementation in a coordinated fashion among DoR and local bodies. | DOR |  | Miscellaneous |  |  |  |  |  |  |  |  |
|  |  |  |  | - Machinery Repair & Maintenance |  |  |  |  |  |  |  |  |
|  |  |  |  | - Purchase of mechanical equipments |  |  |  |  |  |  |  |  |
|  |  |  |  | - Road Transport Security, Control of Encroachment and Border Security |  |  |  |  |  |  |  |  |