### Business Plan for Department of Road

### Table of Contents

Page

### Development Context and Background 	1

### Sectors vision and goals, objectives and priorities of DoR	1

2.1	Vision			         			       				           1

2.2 	Objectives							        		           2

2.3 	Long Term Objectives and Priorities				         	           	           3

### Major problems, challenges and opportunities	3

3.1	Opportunities					          	           			           6

### Key objectives and Quantitative Targets	8

4.1	Objectives								       	           8

### Strategies, Policies and Actions                                                                                                    17

5.1	Strategies									         17

5.2     Working policies 								         17

### Core programs	17

  - Roads connecting the district headquarters 					         17

  - North- South trade and Transit Road		         				         19

  - Mid- Hill Road 						                                                20

  - Kathmandu Valley Road extension					                      20

  - Road Upgrading and Strengthening 						        20

  - Road construction and improvement                                                                                  20

  - Bridge Construction                                                                                              20

  - Repair and Maintenance works of Roads and Bridges 			        21

  - Study and Research 								        21

  - Miscellaneous 									         21

### Budget Allocation	29

### Institutional Development	35

### Monitoring and Evaluation	35

### Critical factors for successful implementation 	36

### Annexure:

### Annex I: The Results Framework for Business Plan (FY 2010/2011-2012/2013)

### Annex II: Framework for Monitoring and Evaluation

- Development Context and Background

- The over-arching goal of the Three Years Interim Plan is to improve the living standards of Nepal's population and significantly reduce poverty incidence through an integrated strategy of faster and equitable growth, human resource and infrastructure development, social and economic integration of disadvantaged communities and reducing regional imbalance. It specifically accords high priority to the road sector for its visible role and contribution to the socio-economic development, social integration and service delivery as well as governance functions of the country. Accordingly, due emphasis was accorded to gradually connecting neighboring India and China through different north-south road corridors and developing the East-West Highway to the level of an Asian Highway, construction and upgrading works for roads connecting district headquarters, remote areas, east-west Mid-Hill & Postal (Hulaki) and north-south Terai roads.

- The approach paper of the proposed TYP appropriately intends to give continuity to the past efforts in the road sector, and recognizes that expected development and standards in the road and transport sector has not been realized.  It is noted that by the end of FY 2066/67 a total of 19,875 km of strategic roads including 6,770 km of blacktop, 3,950 km of gravel and 9,155 km of earthen roads have been constructed so far. Similarly, 1,313 nos. of bridges are in place and 71 district headquarters are connected to the strategic road network. In order to administer and manage the development of roads, roads are classified into Strategic Road Network (SRN) and Local Road Network (LRN). SRN comprises of National Highways, Feeder Roads and strategically important urban links and its responsibility lies with DoR. LRN comprises of District, Urban and Village Road Networks and its responsibility lies with respective District Development Committees / Municipalities / Village Development Committees under the coordination of Department of Local Infrastructure Development and Agricultural Roads (DOLIDAR). In addition, 22,000 km roads have been identified as village roads, which are mostly seasonal and include short non-through roads linking single villages to roads of a higher class.

- The business plan should be viewed as a forward-looking document, which would be updated annually as a part of the Medium Term Expenditure Framework (MTEF) process.  This would enable adjustments/revisions to be made in sector/sub-sector strategies, policies, programs and core activities on the basis of implementation experience and any changes in priorities. This business plan, based on the performance evaluation of TYIP (2007-2010) and covering the plan period of TYP (2010-2013), seeks to present clearly and concisely the Government's (DoR) vision for road sector, the goals and outcomes it seeks to achieve, and the strategies, policies and key programs/activities which will be adopted to achieve these outcomes.

- The business plan begins with the Government's vision for the road sector.  It then outlines the key targets of the TYIP, reviews implementation performance in the last 3 years, and evaluates the likelihood of achieving the targets in the next TYP period.  Drawing on the lessons learned from recent experience, the TYP policies and strategies are reviewed and sharpened to incorporate changes, including amendments to the legal framework, which are necessary for ensuring that the Plan outcomes are achieved.  The core business activities, resource requirements for them, as well as identified funding gaps for the next three years are discussed in the next two sections.  The last two sections discuss the modalities for monitoring progress and the key challenges, which need to be addressed for effectively implementing the business plan.

- Sectors vision and goals, objectives and priorities

2.1      Vision

- The overall goal of road sector is to reduce poverty through socio-economic development by providing equitable, safe and affordable public road infrastructures. This is to be achieved through building and managing road network within the country in least cost and efficient manner.

- The vision of the Road Sector is:” managing roads for national integration and socio-economic development” for the people of Nepal.

- The vision for the development of Strategic Road Network is: To provide sustainable and efficient road service by managing main arteries of the road network; provide links to rural roads, and increase connectivity in potential touristic, hydropower and natural resources development areas and along international trade routes.

- The mission of strategic road development is to contribute towards the betterment of living conditions of the people through effective, efficient, safe and reliable road connectivity.

  - Objectives:

- The objectives of the road sector (DoR) are:

- To maintain road network effectively and efficiently (Asset Preservation)

- To provide access to all district headquarters to strengthen social, economic and administration linkages

- To improve existing access to district headquarters for safe, reliable and cost effective travel

- To develop roads to supplement poverty reduction, program and to improve accessibility to mid-hills and terai.

- To develop and expand the existing Strategic Roads Network (SRN) to facilitate effective and efficient movement of goods and services and to foster economic growth;

- To develop and adopt cost effective measures by initiating innovativeness in road pavement and bridge design

- To develop roads to support other infrastructure development and to link areas of significance social and economic importance; and

- To encourage private sector participation in the development maintenance and management of roads.

- The 20 year Master Plan for the SRN (2002 – 2022), envisages the following outcomes by 2022:

- Motorable access to all 75 District Headquarters in the country with Bituminous sealed road to almost all District HQ;

- Doubling of the length of the present Strategic Road Network with a target road density of 15 km per 10,000 populations;

- Ensuring  more than 95 percent of SRN in a good/fair  condition;

- Substantially reducing the walking distance from 13 days to 3 days in extreme cases to reach the motor-head in High Himalayas & Mountains; and reducing walking distance of 4 hours to reach motor-head in Hills and 2  hours in Terai;

- Establishment and functioning of Autonomous Road Agency to manage central road network with increased level of user's involvement;

- Establishment and functioning of monitoring system for an effective and efficient service delivery through an independent annual user's satisfaction survey; and

- Substantial reduction in the rate of accidents.

- The Sector Wide Road Program in the form of 10-year Priority Investment Plan (2007-2017) has been approved and is being implemented. The feasibility studies for eight identified north to south road corridors are being undertaken, and at the same time, construction and upgrading works in a substantial portion of these roads have already been completed under the pre-text of different programs such as the one connecting various district headquarters.

2.3   Long Term Objectives and Priorities

- In the context of achieving the overstretching national objective of reducing the regional imbalance and social inequality, the long-term vision of the road sector is to develop a safe, reliable and environment friendly national transport network, so as to:

- Provide easy access to agriculture, industrial and other production and service centers.

- Promote trade between the neighboring countries.

- Provide support to the development of other social and economic infrastructures.

- Following specific measures have been conceptualized to meet the aforementioned goals:

- In accordance with the Sector Wide Road Program (2007-2017), develop a minimum 31,000 km. of road network including 9,740 km. of Strategic Road Network (SRN) and 6,000 km. of Local Road Network (LRN), which will provide access to the population living within four hrs. in hills and two hrs. in the Terai, from the road head.

- Develop the identified eight trade and transit corridors between neighboring India and China.

- Develop a transparent and decentralized management system by enhancing the capacity from central to local level entities for prompt construction and maintenance of the roads.

- Develop and operate safe roads by suitable road safety and traffic management activities including raising public awareness on such activities.

- Develop feasible, alternative, transparent infrastructures like railways, ropeways and waterways

- Major problems, challenges and opportunities

- The TYIP targets and expected outcomes, the most recent achievements in the first two years of the Plan and the causes for performance gap during the TYIP plan period are presented in Table 1 below.

Table 1: Performance Gap Analysis

(For FY 2064/065 and 2065/066)

| S No | Outcomes/ Results | Major Program | Target | Achievement | Performance Gap | Causes for Gap |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Twelve district HQs is connected to the road network | • Program for construction of roads connecting DHQs. | 12 District HQs connected | 8 District HQs connected | 4 District HQs yet to be connected(*) | 1. Remoteness/difficult terrain 2. Alignment dispute 3. Budget Constraints 4. DoR capacity 5 Ambitious program |
|  |  | • Program for the upgrading of roads connecting DHQs. | 16 District HQ connecting Roads upgraded | Only one District HQ connecting Road Completed. Others are in various stages of upgrading. | 15 Roads yet to be completed | 1. Delay in loan and grant agreements 2. Budget constraint 3. Capacity of local contracting industry (Contractors/Consultants) 4. DoR Capacity 5. Strike by local political parties 6. Shortage of experienced technical manpower in the country |
| 2 | Connectivity to China and India is enhanced and the operational efficiency of ICDs is improved | • Galchhi-Trishuli-Syaprubesi Road Project. | 84 km Road upgraded | 20% complete | 80% yet to be completed | 1. Delay inland acquisition; dispute in land acquisition. 2. Public demand for double lane road. 3. Local strike |
|  |  | • Tanakpur Link Road Construction Project | 14 km Road Upgrading complete | Yet not started | 14 km Road Upgrading | 1. Delay in grant agreement |
|  |  | • Projects under Sub-regional Transportation Facilitation Project | 1. Bhairahawa-Parasi-Bhumahi (29km) and Birgunj Bypass (10.3km) Roads completed 2. ICD at Kakarbhitta completed | 1. Bhairahawa-Parasi-EWH: 75% complete. 2. Birgunj Bypass: 85% complete 3. ICD : 90% complete | 1. 25% remaining 2. 15% remaining 3. 10% remaining | 1. Delay in Loan agreement 2. Land acquisition Problem 3. Local Bund/Strike 4. Demand for donation by local political parties |
|  |  | • Mahakali Highway (Darchula-Tinkar section) Project | 90km Road | 3km track opened | 87 km | 1. Land acquisition and resettlement Problem at Khalanga Bazaar. 2. Difficulties to transport heavy Equipments |
| 3 | Transport service to Kathmandu valley and other parts of the country is expanded and improved. | • Feasibility Study of the Kathmandu Terai Fast Track. | Feasibility Study completed | Complete | No gap | The opening of earthen track initiated through Nepal Army |
|  |  | • B. P. Koirala Road (Sindhuli Bardibas) Project | 160 km Road Construction | 97 km BT; 26km Gravel; 37km Track |  | 1. Delay in bilateral agreement 2. Local Bund/Strike |
|  |  | • Kathmandu Valley Urban Road Development Program | Improvement of high volume traffic roads within KTM Valley. | Several road sections such as Solteemod-Kalanki-Nagdhunga, Bagmati corridor, Dhobikhola corridor were improved. |  |  |
| 4 | Accessibility to the Terai and dense settlements in the hills as well as administrative, commercial and industrial centers is improved and facilitated. | • Terai Road Improvement Project | 850 km of Road upgraded | IEE for16 Roads under Ist Phase complete. | Construction work yet not started | Agreement between GoN and GoI yet not finalized. |
|  |  | • Upgrading works under RSDP and RCP | RSDP : 278 km Otta Seal RCSP : 358 km BT | RSDP: 125 km OS ; 80 km Gr; 73 km Er RCSP: Started in FY 065/66 | RSDP: 153 km OS RCSP: 358 km BT | 1. Due to late implementation, contracts under RSDP and RCSP are still ongoing. 2. Land acquisition Problem (People's demand for higher value of land and houses) 3. No outlet for side drain due to cultivated land along the road alignment. 4. RSDP Contracts will be completed by FY 066/67 and RCSP contracts by 067/68. |
|  |  | • Upgrading works under RNDP – Fourth Road Improvement | 310km Upgrading; 81km new construction; 280km Performance based Maintenance | All roads completed except Basantapur-Mudhe Section(13km) | 13 km | 1. Slow progress by the contractor 2. Frequent local and Nepal Bund/Strike |
|  |  | • Repair, Maintenance and Improvement of Arniko Highway |  | Annual target of Repair and Maintenance completed |  |  |
| 5 | Accessibility to the transport service for the people of remote areas improved and east-west transport facility extended in the mid-hills. | • Mid-Hill Highway Project | 53 km new construction and 60 km upgrading | 80 km track opened | Upgrading remained. |  |
|  |  | • Road construction under central level sequential list | Er: 475 km Gr: 254 km BT: 53 km | Er: 545 km Gr: 240 km BT: 48 km | Er: No gap Gr: 14 km BT: 5 km | 1. Frequent Nepal Bund, Terai Bund 2. Scarcity of construction Materials 3. Load shedding 4. Lack of coordination with road users' committees |
|  |  | • Bridge Construction Program | 104 bridges will be constructed | 40 bridges completed | 64 Bridges | 1. Insufficient budget allocation 2. Delay in detailed Design and soil investigation 3. Delay in procurement of contracts |
| 6 | Through the preservation of road assets, there is an increase in safe and reliable transport facilities. | • Regular Repair and Maintenance Program | 7220 km SRN will be maintained | 7220km maintained | No gap |  |
|  |  | • Periodic Maintenance Program | 630 km Road will be resealed | 389.5 km Road resealed | 240.5 km | 1. Late procurement 2. Delayed mobilization by the contractors |
|  |  | • Emergency, Major and Special Repair and Maintenance Program | 7220 km SRN will be maintained | 7220 km | No gap |  |

Source: DoR; 2009/10.       Note: (*) – District HQs not yet connected Humla, Dolpa, Manang and Mugu.

- Some of the key constraints faced included the following:

- Ineffective management of road asset due to budget constraints.

- Less time available for construction of important roads and bridges due to wastage of time in budget relocation process.

- Lack of budget and other problems in relation to land acquisition.

- Inadequate skilled human power for supervision of construction and rehabilitation works.

- Non-implementation of road safety concepts.

- Implementation of non-prioritized projects due to political interference.

- Institutional strengthening of the DoR and other related entities not effective yet.

- Ineffective implementation of arrangement for devolution of responsibility to the local bodies for the construction and maintenance of local level roads.

- Lack of a conducive environment to attract private investment in the road sector.

- Ineffective M&E by the regional wings due to inadequate resources, facilities and lack of management infrastructure.

- Thus, in the context of the TYP, the major challenges can be outlined as to the need to (i) develop urban roads and highways in commensuration to increased road traffic, (ii) attract private sector investment in the development of roads (introduction of BOT etc.) (iii) inadequate budget allocation for national level prioritized road projects, (iv) upgrading and construction of bridges on tracks connecting district HQs for safe and reliable transport services, (v) investments for management and preservation the existing road assets in an effective manner, and (vi) implementation of road safety and sustainable road development concept, and (vii) efficient utilization of available resources.

  - Opportunities

- The major opportunities for DoR are as follows:

- Gradual improvements in the performance of the DoR (operationalization of MfDR etc.).

- Gradual improvements in the resource base and management of the Roads Board.

- Capacity enhancement of the local contractors and the consulting organization.

- Improvement in the awareness of road related stakeholders.

- Improvement in the peoples' participation.

- Improved opportunities for resource mobilization and donors' assistance in road construction and maintenance.

- Improved involvement of the private sector in road maintenance (PBMC system).

- Increased acceptance of e-procurement by all stakeholders.

- Some of the recent implementation experience and lesson learnt has been elaborated in the ensuing paragraph as below;

- Priority for maintenance: GoN has established an autonomous Roads Board and Road Fund to provide stable funding for road maintenance from user fees. Roads Board has generated about one third of the resources required to fulfill the resource requirement for the maintenance of the Strategic Road Network (SRN) in Nepal. The Board is facing managerial problems on not being able to make appointment of necessary staff due to low salary structure, autonomy for adopting MoPPW official process for Board decisions and delivering responsibilities of MOLD/DOLIDAR in technical backstopping for planning and managing rural road maintenance by the local bodies and their timely monitoring and reporting. Considering the cost of rehabilitation, which is about five times the maintenance cost, Roads board needs to develop efficient and effective planning as well as funds releasing mechanism.

- Expanding the Strategic Road Network. The road network in Nepal has increased from 7000 km in 1990 to 16000 km in 2003. GoN has targeted to link additional 10 District Head Quarters to road network by 10th plan period.

| - Year | - Highway | - Feeder Road |
| --- | --- | --- |
| - 1995 | - 2831 | - 1679 |
| - 1998 | - 2905 | - 1826 |
| - 2002 | - 3029 | - 1832 |

- Source: NRS 1995, 1998, 2002

- Increasing and Prioritizing Investment Nepalese investment in road sector is far less than what is necessary. In order to facilitate the 6.3% GDP growth anticipated in the Tenth Plan, it is necessary to invest about 2% its GDP (about US$115 million a year) on expanding its road network to remove transport impediments for its economic growth, and another 1% of its GDP (about US$30 million a year) on maintaining existing assets. In sum, it is necessary to invest about 2.5% of its GDP (about US$145 million a year) in expanding and maintaining road assets. These estimates are substantially higher than the current expenditure in the road sector, where GoN in 2003 spent about US$30 million for new investment and US$25 million for maintenance and rehabilitation.

- Promote private sector participation (PSP) in road development. Experience in other countries suggests that the private sector is unlikely to deliver road sector projects without substantial government involvement in the form of enabling legislation and regulations, proper institutional arrangements, provision of land, environmental and social protection, and possibly financial guarantees and/or some measure of co-financing.

- Road development with support of road users. In some of the road construction projects practice of mobilizing road users in form of RBG* and CBOs** has already been started, such as in the projects supported by WB and DFID (Surkhet- Jumla Road Project, Hile –Bhojpur Road Project). Such concept of road construction is expected improve income level of the people living in the influence area by generating additional employment opportunities in local level. The constraints and limitation in such practice are the technical competence as well as the managerial capability of the local involved. This demands introduction of awareness as well as training program to the local RBG and CBOs to enhance their skill, capacity and managerial capability. However, the efficiency, effectiveness and sustainability of the running projects are yet to be observed.

- Rural Roads and Decentralization. According to existing decentralization framework, the concerned districts are responsible for administering and financing of rural roads (comprising district roads, village roads, and agriculture roads). Substantial lengths of new rural roads have been constructed in recent years mobilizing communities without any quality assurance and no record maintained on the length and condition of these roads.  Many donors (DFID, ADB, SDC, GTZ, WFP, and USAID) are supporting rural roads construction and managed by the local bodies (some districts) in a projectized approach. The lack of a clear strategy towards developing sector wide rural transport to provide minimum equitable motorable access in the country has led more unbalanced developments and less effective investments. In addition, HMGN has been providing resources to local bodies for the development of rural roads. However, efficient and effective monitoring mechanism is yet to be developed towards achieving the targeted outputs. Further, MLD/DOLIDAR is undertaking rural road development activities in form of agricultural roads and food for work program. In FY 2004, GoN announced LID policy with an objective to enhance social service and economic opportunities through mobilizing resources among the local people. The LID policy aims to devolve all infrastructures through concerned local agencies. The new policy also explains that all the agricultural and local roads will be categorized as rural roads. Accordingly, MLD/DOLIDAR has developed a rural transport sector strategy with a policy to develop all weather motorable access in the rural area within 4 hours walking distance in hill and 2 hours walking distance in the Terai. In this regard, every district shall prepare District Transport Master Plan (DTMP) through participatory process to identify and prioritize inter-district rural roads to provide all weather access as envisaged by LID policy.  A long term Rural Transport Plan up to 2017 (end of 12th Five Year Plan) will be developed under this plan.

- Urban Transport: Urban Transport is one of the neglected sub-sector due to fragmented responsibilities (DoR and Local Governments) and weak fiscal and implementation capacities of local bodies. The main problem in urban transport is traffic congestion and constrained transport infrastructures. With rapid urbanization, the problem is expected to become more complex in coming days.

- Institutional Reforms and strengthening: The responsibilities in road sector are shared between five entities, with overall GoN coordination and oversight exercised by the National Planning Commission (NPC).  These entities are the Ministry of Physical Planning & Works (MoPPW), the Department of Roads (DoR), the Ministry of Local Development (MOLD), the Department of Local Infrastructure Development & Agriculture Roads (DOLIDAR), Municipalities, individual District Development Committees (DDC) and Village Development Committees (VDC).  The former two entities are responsible for national road network; the Department of Roads has been entrusted with responsibility of SRN.  The latter three entities share various responsibilities in the development and maintenance of district-level roads. These entities are affected by varying capacity, weaknesses, structural and organizational constraints and are in need of strengthening. Cost effectiveness in planning, timely decisions and quality of works are major concerns. The central level supporting units are virtually non-functional except for routine works. In addition, the prevailing environment within the country has demanded changes in planning and implementation approach towards comprehensive. However, the concerned agencies are not yet ready for.

- Although the DoR has made considerable progress in key aspects of its technical and managerial capacity building plans, the department however continues to be reliant on significant donor support to discharge its primary responsibilities. The department is lagging behind in extending the application of internationally accepted practices, processes and technology on a more sector-wide basis.  Its HQ-based policy, monitoring and support units are inadequately resourced for their ascribed functions and are understaffed. Such institutional realities demand drastic modernization of DoR into a modern and effective road management agency while Dolidar and local bodies for wider road network development in rural areas.

IV     Key objectives and Quantitative Targets (three years perspective)

4.1    Objective

17.  The main objective is to extend the transport network to contribute to national economic and social integration, regional balance and regional development.

Expected major outputs include the followings ;

- All district headquarters to be connected to national road network and movement to additional 20 district headquarters to be facilitated with the upgrading to the level of black-topped roads.

- Construction of mid hill Lok Marga and Kathmandu Terai fast track to have been completed.

- Additional 200 numbers of bridges to be constructed.

- Regular repair and maintenance of 9,400 km of roads and periodic repair and maintenance of 3,600 kms of road to have been accomplished.

- 1,044 km of new road would be constructed.

Table 2: Outcomes/Results and Quantitative Targets for TYP and Business Plan Period- DoR

| Major Programs wrt Sectoral Outcomes | Outcome Indicators | Agencies/ Dept./PEs/ Divisions | Sub- programs / Projects |  |  | Output Indicators | Baseline FY 2066/67-(2009/10) | Business Plan – Yearly Output Targets & Progress |  |  |  |  |  |  | Total -3 yrs |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Road Section | Tot.-km |  |  |  | Target FY 2067/68 (2010-11) |  | Target FY 2068/69 (2011-12) |  | Target FY 2069/70 (2012-13) |  |  |  |  |  |  |  |
| - Programs for Roads Connecting District Headquarters and its upgrading. Outcome: Access to all the district headquarters of Nepal facilitated. | - No. of DHQs connected to road network - Additonal population within the reach of 2 to 4 hours walking to the road access No. of new settlements connected with road. | Nepal Army & DoR | 1. New Road Construction - Nagma-Gamgadhi : 91 km - Jajarkot-Dunai(Dolpa): 144 km - Besisahar Chame: 65 km - Karnali: Hilsa – Simikot under North South Lok Marg : 88 km |  |  | - Length of Earthen Track Opened -km. | 176 | 55 |  | 40 |  | 34 |  |  | 129 |  |  |  |  |
|  | - No. of DHQs with year round road accessibility 8+5+4+5= 22 - Reduction in the time to travel up to the DHQ. - Reduction in transportation cost of different goods and services. | DoR | 1.2 Road Upgradation for DHQs - Road Improvement Project (RIP) - 8 DHQs- incl. Salyan, Dailekh, Bajura, Achham, Terhathum, Khotang, Pyuthan & Myagdi.-484 km - RSDP I & II -including 5 DHQs Darchula and Bajhang, Jumla, Jajarkot & Rukum – 512 km - Sub-regional Transpor Enhacement Project including 4 DHQs of Okhaldhunga, Solukhumbu, Sankhuwasabha, Bhairahwa.-185 km - 5 DHQs under Road Connectivity Project I + Sunkoshi Bridge Rasuwa, Ramechhap, Dhanusha, Taplejung, & Kapilvastu, -317 km |  |  | - Length of new BT paved road section – km - Length of BT-Rehabilitation and Strengthening works -km | 228 | 25 517 |  | 20 338 |  | 45 383 |  |  | 90 1,238 |  |  |  |  |
| - Programs for improving accessibility in dense settlements of terai and hills as well as administrative, commercial, tourism and industrial centers. Outcome: Access to terai and hills cluster settlements and add administrative, commercial, tourism and industrial centre to be convenient. | - Additonal population within the reach of 2 to 4 hours walking to the road access - No. of new settlements connected with road. - Increase in road intensity. - Reduction in travel time for east west travel in the mid hill areas - Reduction in travel time for travel between Kathmandu and terai. - Increase in access to social services such as education, health. | Nepal Army & DoR | 2.1 North-south trade and transit roads. - Kathmandu-Tarai-Madhesh Fast Track -77 km - Banglung Beni Jomsom-97 km - Syaphrubesi Rasuwagadhi-16 km - B P Koirala Lokmarg (Banepa-Sindhuli-Bardibas)-160 km - Mahakali Lokjmarg (Darchula-Tinker Section)-90 km - 4 NS trade & Transit Roads under RIP (6 lane widening of 4 road sections namely (i) Rani Itahari-Dharan 50km (ii) Birgunj Pathlaiya 28km, (iii) Beliya-Butwal 24 km, (iv) Suryabinayak-Dhulikhel 16km. - Sankhu Melamchi & Tokha-Chhahare under Road Improvement Project(RIP) (included under RIP in 1.2 as above)-58km - 7 North-South Roads along Karnali, Kaligandaki & Koshi-931 km |  |  | - Length of Earthen Track Opened -km. - Length of Gravel works -km. - Length of new BT paved road section – km - Length of BT-Rehabilitation and Strengthening works –km - Land acquisition and other activities - Curve & grade improvement, repair & maintenance and drain & structures works - No. of Surveys and DPRs - No. of bridge design and EIA - No. of bridges |  | 150 14 20 0 9 |  | 132 54 13 0 0 |  | 140 108 24 0 9 |  |  | 422 176 57 0 9 |  |  |  |  |
|  |  | Nepal Army & DoR | 2. 2 Mid Hill Road Development Program - Musikot-Burtibang – 145 km - Puspalal Lokmarg (Mid Hill Lokmarg) -180 km |  |  | - Length of Earthen Track Opened -km. - Length of Gravel works -km. - Length of new BT paved road section – km |  | 234 15 0 |  | 6 15 140 |  | 4 20 150 |  |  | 244 50 290 |  |  |  |  |
|  |  | DoR | 2.3 Upgradation of Postal (Hulaki) and other roads of strategic importance - Postal Roads including Bridges (Phase I only, Total three phase 1500km)-640 km - Rapti Lokmarg (Sallyan-Musikot Blacktop) – 86 km - Kanti Lokpath -93 km - Naradmuni Thulung Marg (Hile-Leguwaghat-Bhojpur)- 93 km - Ganeshman Singh Marg(Thankot-Chitlang) – 20 km - Byas Marg – 31 km - Dharan Chatara Gaighat Katari Sindhuli Bazar-Hetauda -325 km - 11 Kilo Chhepetar Bhaluswara Warpak -53 km - Fikkal Shree Antu Danda Road - Dakchinkali Chaimale Sisneri Kulekhani-19 km - Road Connectivity Project II (Pdirect.& Consultancy Services and road upgrading)-300 km |  |  | - Length of Gravel works -km. - Length of new BT paved road section – km - Length of BT-Rehabilitation and Strengthening works –km - No. of Surveys and DPRs - No. of bridge design and EIA - No. of bridges |  | 65 64 0 NA NA 5 |  | 47 219 0 NA NA 16 |  | 50 479 0 NA NA 18 |  |  | 162 762 0 NA NA 39 |  |  |  |  |
|  |  |  | 2.4 New Road Construction and Extension - Sagarmatha Lokmarg (Gaighat- Diktel Section) -131 km - Seti Lokmarg ( Tikapur-Lode-Chainpur-Taklakot) - Survey & EIA for 40 km to be done for each of three years – 285 km - Tourism Roads - 23 road sections for upgrading and new construction - Central Level (Various phase-wise roads) - Regional Level Roads (34 plus 40 Nos) - Gangate Labhdu Samudratar Galfu Bhanjyang -63 km - Saljhundi Sandhikhark Dhorpatan Road -128 km - Chepang Marg (Bhandara-Lothar-Malekhu) -60 km - Tanakpur Link Road -14 km - Sahid Marg (Tila Ghartigaon Thawang Rukumkot) - track to be opened upto MHH -177 km - Benighat Aarughat Larkebhanjyang -130 km - Tallo Dhungeshore Satkhamba Dullu Pipalkot Dailekh -33 km - Gumi -Patihalna Chour (Surkhet) -45 km - Mirdi Kyakmi Bhimad -59 km - Putalikhet-Karkineta-Kusma -47 km |  |  | - Length of Earthen Track Opened -km. - Length of Gravel works -km. - Length of new BT paved road section – km - Land acquisition and other activities - Curve & grade improvement, repair & maintenance and drain & structures works - No. of Surveys and DPRs - No. of bridge design and EIA - No. of bridges |  | 250 85 53 |  | 277 111 51 |  | 220 133 64 |  |  | 747 329 168 |  |  |  |  |
|  |  | DoR | 2.5 Bridge Construction Program - Bridge Construction along the Postal Roads - Sunkoshi Bridge (Road Connectivity Project I) |  |  | - No. of Surveys and DPRs - No. of bridge design and EIA - No. of bridges | Total 227 bridges under construction | - Refer section 2.3 above under Postal Roads - Refer section 1.2 above under Road Connectivity Project |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Bridge Construction Program |  |  |  |  | 45 | 50 |  |  |  |  |  |  | 55 |  | 150 |  |
|  |  | MoPPW | - Koshi Bridge (Chatara) (Flood Damaged Reconstruction Project) |  |  |  |  | Bridge construction at Chatra to continue | Bridge construction at Chatra to continue Bridge construction at Chatra to continue |  |  |  |  |  |  |  |  |  |  |
| - Programs for expansion and improvement of transport facilities in the Kathmandu Valley and other urban centers of the country | - Travel time within Kathamndu Valley to be reduced. - Redcution in air pollution. - Reduction in the number of road accidents. - Development of handicapped- friendly road structure. | DoR | 3.1 Urban Road Improvement Program - Kathmandu Bhaktapur Road Extension - Kathmandu Valley Road Construction and - Kathmandu Valley Road Extension Project - Other Urban Roads |  |  | - Length of Earthen Works -km - Length of Gravel works -km. - Length of new BT road section – km - Length of BT-Rehabilitation and Strengthening works –km - Length of river training works-km - Extent of re-plotting land parcel and distribution of land ownership certificate |  | 10 0 87 62 | 0 10 105 10 |  |  |  |  | 0 15 110 10 |  |  |  | 10 25 302 82 |  |
|  |  | MoPPW | - Kathmandu Sustainable Urban Transport Project - PIUs of MOEnv, DoR, KMC, DOTM & MTPD |  |  |  |  | Mobilization – selection of consultants | Capacity building of PIUs, |  |  |  |  | Constr. of Bus stops, lay-bys, shelters and route improv . & CCTV |  |  |  |  |  |
|  |  | KVTDC | - Dhobikhola Corridor Improvement Project including 9 km wide road on both side of the river - Replotting the land parcel and distribution of land ownership certificate |  |  |  | Track 3.4 km & RT 0.74 km | 2.4 | 2.74 |  |  |  |  | 2.68 |  |  |  |  |  |
|  |  | HPC for IDP - BAIDP | - Road Construction at Gokarna- Sankhamul Stretch ( 10 km |  |  |  | 1.5 | 1.5 km | 5.5 km |  |  |  |  | 4.5 km |  |  |  |  |  |
| - Programs for Feasibility studies and R&D on alternative transport (railways, waterways, ropeways etc.) system as well as on road safety. |  | DoR | - Detailed Feasibility Studies of Roads and Bridges |  |  | - No. of studies for transport development based on alternative technology. - No. of feasibility studies done for road infrastructure development. - No. of studies and reserach on road safety. | NA | NA | NA |  |  |  |  | NA |  |  |  |  |  |
|  |  |  | - Planning, Program, M & E, Geo-environment studies etc. |  |  |  | NA | NA | NA |  |  |  |  | NA |  |  |  |  |  |
|  |  |  | - Transport Project Preparatory Facilitation (Feasibility & Design ADB) |  |  |  | NA | NA | NA |  |  |  |  | NA |  |  |  |  |  |
|  |  | MoPPW | - Water Way Project |  |  | - No. Of feasibility studies and length of river covered for water ways - Length of rivers channels free of obstructions - No. Of waterway stations and platforms constructed. |  | - 2 & 100 km | - 3 & 450 km - 100 km - NA |  |  |  |  | - 5 & 500 km - 450 km - NA |  |  |  |  |  |
|  |  | DoRail | DPR of Railway Track |  | 1200 | - No. Of DPR for railways |  | Preparation of DPR for Mechi to Mahakali -945 km, and Pokhara to Kathmandu – 187 km railway track as well as required link tracks. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - New Construction of Railway Track |  | 200 | - Length of Railway Track constructed |  | Pre construction and commencement of construction works for new railway tracks connecting Indian Border. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | - 88 km |  |  | - 74 km |  | - Other Links -38 km |  |  |  |  |  |  |
| - Program for Road Strengthening and Repair Maintenance | - Reduction in the operation cost of vehicle. - Reduction in travel time and transportaion cost. - Reduction in road accidents - Smoothness in the operation of transport service. - Strengthening and use of statistical base of DoR including local bodies. - Estab. and utilization of road asset protection system - Effectiveness of the maintenance fund under the Road Board. - Length and operation status of the road transferred to the local bodies. | DoR | - Karnali Lokmarg (Surkhet- Jumla) |  | 232 | - Length of road under periodic maintenance - Length of stretch for grade & curve improvements - Length of stretch for regular repair & maintenance - No. Of bridge repaired |  | Out of 232km, 126 km under RSDP for upgrading, rest between Kalikot-Jumla 106km track for curve & grade improvement |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Jaya Prithvi Bhadur Singh Marga, Khodpe bajhhang |  | 110 |  |  | Out of 65km track, 45 km under RSDP for upgrading and curve & grade improvement, repair & maintenance for rest of track. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Damak Chisapani |  | 44 |  |  | 3 km GR in 2067-68 and 4km GR for next 2 years plus Grade & curve improvements, const. of Structures, repair & maintenance |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Bridge-culvert Conservation and Maintenance & Repair |  |  |  |  | 9 bridge in SRN to be repaired, historical data on SRN & FR bridges to be collected |  |  |  |  |  |  |  |  |  |  |  |
|  |  | MoPPW | - Flood Damaged Reconstruction Project |  |  |  |  | Repair & maintenance |  |  | Repair & maintenance |  |  | Repair & maintenance |  |  |  |  |  |
|  |  | RBN | - Road Boards Strategic Roads Periodic Maintenance |  | 1950 |  |  | Periodic Maintenance -400 km |  |  | Periodic Maintenance -700 km |  |  | Periodic Maintenance -800 km |  |  |  |  |  |
|  |  |  | - Road Boards Routine, Recurrent and Emergency Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Nepal Army | Grade & curve improvements, repair & maintenance for - Chhinchu Jajarkot - Devasthal-KanaiDanda-Chaurjhari |  |  | - Length of stretch for grade & curve improvements - Length of stretch for regular repair & maintenance |  | - part of 45 km - entire stretch |  |  |  |  |  |  |  |  |  |  |  |

- Strategies, Policies and Actions to Achieve Key Objectives/Targets Strategies

  - Strategies

18.  The Strategies for  DoR as follows:

- To extend transport access and facility in such a way as to connect regional and district headquarters.

- To extend transport to enhance employment through increase in access to agriculture, industry, hydro-power, education and health services.

- To develop and extend roads according to vehicular pressure.

- In addition to road transport, to extend other modes of transport including railways on the basis of feasibility studies.

- To promote PPP in transport infrastructure development.

- To make road asset protection and management more effective.

- To develop sustainable, safe and reliable transport network.

5.2   Working policies

19.  The major working policies for DoR is  as follows:

1.1	District headquarters including Humla that are not yet connected to road network will be connected with road network.

1.2	The road network connecting with district headquarters and other roads of national importance will be in a gradual way, upgraded to make them operate for the whole year.

1.3	  North-South roads will be constructed and upgraded in such a way as to connect border trade centres and major entry-port with Lok Marga along with the upgrading of postal roads.

1.4 	Auxiliary roads and district roads will be constructed, extended and upgraded in addition to pushing forward the construction work of mid hill Lok Marga and Kathmandu Terai fast track.

2.1 	Priority will be accorded to roads nearing completion and roads that generate employment opportunities. At the same time, use of the local technology will be encouraged.

2.2 	Roads that provide support for important hydro-power, irrigation, tourism and industry and that help to increase access to agriculture, education, and health will be constructed and upgraded.

3.1	  In order to extend the capacity of Lok Marga and urban roads according to the vehicular pressure, works such as widening of roads, crossing improvement, flyover, tunnel way, and alternative road construction will be accomplished.

3.2 	Considering, the pressure of urbanization in Kathmandu Valley, road network will be extended to help support transport management that is safe, environment- friendly, and free of obstructions.

3.3	  The technical shortcomings seen in the implementation aspects of the existing standard of road sector will be gradually improved by formulating necessary law and policy in order to make the road construction work in urban areas well managed.

3.4	   While constructing roads, infrastructure such as drainage, drinking water, electricity, telephone will be separately arranged on either side of the right of way of the road. Provisions will be made for footpath and bicycle lane in roads wherever possible.

4.1	  The development of east west and Kathmandu Pokhara electric railway will be pushed forward based on feasibility by constructing the necessary organizational structure.

5.1	   In order to develop alternative transport system such as waterways and ropeways that are considered important even from the tourism point of view, investments will be encouraged to be attracted through the concept of PPP, BOOT/BOT.

5.2	   Investment plan will be prepared for the development of other transport network including big roads of national importance.

6.1	   The capacity of agencies, local construction entrepreneurs and consultants affiliated with road construction and maintenance will be enhanced in order to ensure low cost, quality road and timely completion of plans.

6.2	   Special emphasis will be given to the periodic repair and maintenance works of road network.

6.3	   Studies will be conducted on the possibility of using road maintenance fund after strengthening the same.

6.4 	Road asset management will be made effective.

7.1	   Handicapped-friendly road structure will be gradually developed.

7.2 	The use of local construction materials and skills will be encouraged while constructing road in order to ensure environment protection.

7.3 	Special attention will be paid to environmental, poverty alleviation, inclusive development and employment aspects while constructing roads.

7.4 	In order to make road construction sustainable, safe, and cost effective, necessary code and specification will be produced and used.

7.5 	In the construction of national priority roads, construction process will be advanced through multi-year contract management.

7.6 	For the sustainable and cost-effective infrastructure development, other necessary structures will be along with the strengthening of Nepecon, Nepal Standard Department established for the preparation necessary documents.

7.7 	Electronic procurement system will be further refined and implemented in road construction and repair works.

7.8 	The responsibility of the operation and repair and maintenance of local roads will be given to local bodies. In addition, based on the road density, the existing human resources, machineries and equipments, hosing building will be transferred to the local bodies.

7.9 	Geographical road data system will be established and implemented by linking all the constructed road statistics constructed by all the agencies.

7.10	The entry as well as the exit in Lok Marga and other important roads will be gradually managed well.

7.11	Necessary reforms will be made in all the laws and rules related with road infrastructure another transport development including public roads act 2031.

7.12	While constructing urban roads, rainwater on the road surface will be used for recharging the ground water.

7.13	By establishing Boot Cell in the department of roads, the PPP program will be advanced.

7.14	By establishing Research and Development section in the Department of Roads, research works will be advanced.

7.15	Constant efforts will be made to take advantage of new technology and the technology found to be useful and fruitful in other countries. Emphasis will be laid on PPP through study and information sharing on tunnel, flyover, LRT, MASS Transit, Metro in other countries.

- Core programs to achieve the objectives and quantitative targets (review of ongoing programs and prioritization)

Major Programs

6.1   Roads connecting the district headquarters

20. Of the remaining four districts  to be connected with district headquarters, Manang, Mugu, and Dolpa will be connected from national road network while Simikot, the district headquarter of Humla, will be connected through road transport from Tibet. During the TYP period, there is a program to upgrade 25 roads given below including the strengthening of two roads already connected with district headquarters to black topped level.

- Under the road sector development plan implemented through the support of the World Bank, six district headquarters Bajhang, Darchula, Kalikot, Jumla, Jajarkot, and Rukum.

- Under the Road Connectivity Project with assistance from ADB, Taplejung, Ramechhap, Nuwakot, Rasuwa and eight districts including Kapilvastu and Okhaldhunga, Solukhumbu, and Sankhuwasabha under Sub-regional Transport Logistic Facilitation Enhancement Project.

- Under the assistance of the government of India, 11 district headquarters including Khotang, Dang, Salyan, Rolpa, Bajura, Achham, Pyuthan, Rautahat, Terhathum, Myagdi, and Dailekh alternative road.

6.2   North- South trade and Transit Road

21.  Since Nepal would be able to take direct advantage if her land is used for smooth movement between India and China, the implementation has been initiated with the identification of various eight trade and transit corridors.

1. Kechana –Ilam – Phidim –Taplejung – Olangchunggola (460 kms)

##7 kms transport from Kechana to Taplejung of Mechi Lok Marga is in operation. Of the 337 kms, 93 kms road portion from Phiddim to Taplejung is in operation under road Connectivity Project Program and will be completed within the Plan period. The remaining road construction of 123 kms from Taplejung to Olangchunggola portion, track construction work has been initiated under the North south road program.

2. Rani – Itahari – Dharan Dhankuta – Hile – Sankhuwasabha – Khandbari – Kimanthanka (419 kms).

329 kms if transport from Rani to Sankhuwasabha of Kosi Lok Marga is in operation. Of the 329 kms, 44 kms of road segment from Chainpur to Khandbari is in operation under Sub-regional Transport Logistic Facilitation Project program and will be completed within the plan period.  The track construction work of the remaining 90 kms of road construction, the segment from Chichilli bazaar to Kimanthanka, has been initiated under the North South Road programs and will be completed within the plan period.

3. Janakpur – Dolakha- Lamabagar – China border area (295 kms.)

The 263 kms transport from Janakpur to Lamabagar of Dolakha district is in operation. The upgrading works from Janakpur to Dhalkebar 25 kms and Tamakosi to Manthali 55 kms segment will be completed under Road Connectivity Project within the plan period. The detailed survey of the remaining 32 kms of road construction has been completed. Track construction has been initiated under the North South Road program from Lamabagar to Falate road segment (China Border area). 77 kms of Fast Track construction work has been initiated to connect Kathmandu with terai.

4. Birgunj – Jitpur –Pathalaiya – Fast Track road from Kathmandu – Dolalghat – Miterisanghhu (292 kms.)

292 kms of transport from Birgunj to China border area Tatopani under North South road is in operation.  With the construction of the fast track, the length of this road will decrease.

5. Birgunj- ICD – Jitpur – Pathalaiya (Mahendra Rajmarga) – Kathmandu Kolfu – Trisuli – Dhunchhe – Syaprubesi – Rasuwa Gadhi ( 265 kms.)

292 kms of transport is in operation from Birgunj (ICD) to Syaprubesi. The upgrading of Galchhi – Trisuli – Syaprubesi, 89 kms segment will be completed within the Plan period under the Road Connectivity Project. Along with this, with assistance from the Government of China, construction work of 16 kms of road from Syaprubesi – Rasuwagadhi to Chinese border will be completed at gravel road level within the plan period.

6. Sunauli – Mirmi – Falebas – Jomsom – Korala 9467 kms)

37 kms of transport form Sunauli to Jomsom is in operation. Track construction work has been started in the remaining 95 kms from Jomsom to Khotang segment under the North- South Road program and will be completed within the Plan period.

7. Nepalgunj – Surkhet – Jumla – Simikot p Hilsa (436 kms.)

Transport from Nepalgunj to Jumla via Surkhet is in operation. About 40 kms of track out of 88 kms of Simikot to Hilsa road segment has been opened by the local body. Of this road, track construction work has proceeded from Rakan Khulalu to Simikot via Hilsa under the North-South Road program with the establishment of an office.

8. Brahmadevmandi – Jog budha – satbanjha – darchula – Tinkerpas ( 415 kms.)

Track construction work has started on the Darchula – Tinker segment under the remaining road construction of 90 kms under the Mahakali Lok Marga. The upgrading of Gokuleshore – Darchula road will be completed within the plan period under the Road Area Development Plan (RSDP).

6.3   Mid- Hill Road

22. The mid- hill Lok Marga starts from Chiyobhanjyang (Nepal India Border) to the east and ends at Jhoolaghat of Baitadi district  to the far west. Of the estimated length of 1,774 kms of this Lok Marga, track opening in the remainging 226 kms will be completd and upgrading will be gradually done.

6.4   Kathmandu Valley Road extension

23. The work of stregnthening the road network is under prgress to make the transport management in places with maximum vehicular pressure within the Kathmandu Valley. In this process, road widening from Kalanki to Nagdhuna will be continued. To reduce the vehicular presure at Kalanki crossing, Kalanki by pass  and for Chabahil crossing bypass  (Golf courde) Bagmati road will be constructed. Under the Kathmandu Valley urban road program, continuity will be given to Bagmati corridor construction work and the managing and extending of the ring road track works. Strengthening, upgrading and repair and maintenance of the major urban roads within the valley will be accomplished. Kathmandu - Bhaktapur road under extension to four lanes will be completed.

6.5   Road Upgrading and Strengthening

24. Out of the current 9,400 kms of road network of strategic significacne,  according to the target of gradually upgrading the roads not yet black topped and mid hills lok marga, road upgrading works will be done with the assistance of donor nations, agencies and from the own source of the Government of Nepal. Out of the 1440 kms, 640 kms of postal roads will be upgraded with the assistance of the Government of India. Planning and Upgrading works through improvement in grade and curves/turns of Dharan- Chatara- Gaighat –katari- Sindhuli Bazaar – Hetauda – Naradmui Thulungmarga, kanti Lokpath, 11 kms of Chhepetar Bhaluswanra Warpak roads are being constructed with the resource of the government of Nepal. Regional roads have been incorprated in the program in order to extend and upgrade roads for increasing easy bazaar access of important tourist sites, agricultural and industrial produce.

6.6   Road construction and improvement

25.  With the purpose of extending road access, the construction and improvement works of other roads including Gaighat – Diktel, Chepang Marga ( Bhandara- Lokhat – Malekhu0, Benighat- Aarughat- Larkebhanjyang, Saljhoondi – Sandhikharka – Dhorpatan, Shahid Marga (Tila- Ghartigaon – Thawang- Rukumkot). Seti Lok Marga (Tikapur- lode – Chainpur – Taklakot) will be carried out.

6.7   Bridge Construction

26. The construction work of 140 bridges lying on the major Lok Margas and auxiliary roads will be completed. Belly Bridge will be purchased to assemble 10 bridges for immediately making the transport smooth over rivers lying on roads where transport operation has been obstructed due to the absence of bridges despite the fact that roads of strategic importance and roads connecting with district headquarters have already been constructed. 60 bridges lying on the Postal Rajmarga will be constructed. In addition, the construction work of the total of 200 bridges including Sunkoshi bridge under the Road Connectivity Project with ADB assistance and Kosi bridge (Chatara) under the Flood-related Damage Reconstruction project will be carried out.

6.8   Repair and Maintenance works of Roads and Bridges

27.  Under this program road structure will be strengthened and well managed through regular, specific and periodic maintenance and repair works of various Lok Margas, auxiliary roads and bridges. In a similar way, works to make Lok Marga and auxiliary roads safe and reliable will be continued.

6.9   Study and Research

28. Feasibility studies of various roads and bridges, detailed survey and design, geo environmental study and institutional strengthening of the DoR will be carried out.

Necessary actions have been taken to establish Estate Management, Contract Management and Quality Control Division in DoR for making construction works effective to maintain quality and to make contracting more transparent, and to protect, manage and sustainable use of road assets in order to make bridge construction works well managed under the institutional strengthening.  At the same time R&D Section will be established to enhance technical capacity. New useful technology will be identified and used. In order to advance PPP programs, BOOT cell will be established.

6.10  Miscellaneous

Road safety, control of encroachment and border safety, compensation distribution, Traffic and safety measure for the above roads, mechanical  equipment and purchase and repair and mainenance works are incorporated under this program.

Table 3: Core Business Activities – DoR

| Major Programs wrt Sectoral Outcomes | Agencies/ Dept./PEs/ Divisions | Sub- programs / Projects |  |  |  |  | Business Plan Actions for FY 2010/11 |  | Business Plan Actions for FY 2011/12 |  | Business Plan Actions For FY 2012/13 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Road Section | Tot. (km) |  | Track km |  |  |  |  |  |  |  |
| - Programs for roads connecting District Headquarters and its upgrading. | Nepal Army | 1.1 New Road Construction |  |  |  |  |  |  |  |  |  |  |
|  |  | - Nagma-Gamgadhi (Mugu) |  | 91 |  | 58 |  | Continue open earthen track - 28 km |  | Complete remaining 5 km earthen track Continue with curve & grade improvement. |  | Continue with curve & grade improvement. |
|  |  | - Jajarkot-Dunai(Dolpa) |  | 144 |  | 23 |  | Continue open earthen track – 22 km |  | Continue open earthen track – 20 km |  | Continue open earthen track – 20 km and remaining 46 km after FY 2012/13 |
|  |  | - Besisahar Chame |  | 65 |  | 60 |  | Complete remaining 5 km earthen track and continue with curve & grade improvement |  | Continue with curve & grade improvement works. |  | Continue with curve & grade improvement works. |
|  | DoR | - Karnali: Hilsa – Simikot (Humla) under North South Lok Marg |  | 88 |  | 35 |  | 35 km track from Tibetan Border operational, Continue open earthen track . |  | Continue open earthen track – 15 km |  | Continue open earthen track – 14 km: remaining 24 km |
|  | DoR | 1.2 Road Upgradation for DHQs |  |  |  |  |  |  |  |  |  |  |
|  |  | - Road Improvement Project (RIP) - (total 17 nos.) including 8 road sections connecting DHQ including Salyan, Dailekh, Bajura, Achham, Terhathum, Khotang, Pyuthan & Myagdi. |  | 484 |  | 204 |  | Complete strengthening of Chapur-Gaur 25 km Continue with BT upgrading works for 249 km (Also refer 2.1 below) |  | Continue with BT upgrading works for 79 km (Also refer 2.1 below) |  | Continue with BT upgrading works for 18 km, |
|  |  | - Road Sector Development Project I & II -(total) including 5 roads connecting DHQs including Darchula and Bajhang, Jumla, Jajarkot & Rukum |  | 512 |  |  |  | Continue with BT upgrading for 28 km. Periodic Maintenance – 165 km |  | Continue with BT upgrading for 122 km. Periodic Maintenance – 70 km |  | Continue with BT upgrading for 275 km. Periodic Maintenance – 70 km |
|  |  | - Sub-regional Transport Enhacement Project including 4 roads connecting DHQs of Okhaldhunga, Solukhumbu, Sankhuwasabha, Bhairahwa. |  | 184.5 |  |  |  | Design, Tendering, Contract award for '- Chainpur Khandbari 43km BT, - Harkpur Okhaldhunga 47 km BT, Okhaldhunga-Salleri 44km BT, Belbari-Chauharwa 47 km BT, Bhairahwa byepass 3.5km BT |  | BT upgrading for 95 km. |  | BT upgrading for 89.5 km. |
|  |  | - 5 roads connecting DHQs under Road Connectivity Project I + Sunkoshi Bridge - DHQs included of Rasuwa, Ramechhap, Dhanusha, Taplejung,& Kapilvastu, |  | 317 |  |  |  | Continue with BT upgrading for 240 km. Continue with Sunkoshi bridge |  | Continue with BT upgrading for 42 km. Continue with Sunkoshi bridge |  | Continue with Sunkoshi bridge |
| - Programs for improving accessibility in dense settlements of terai and hills as well as administrative, commercial, tourism and industrial centers. |  | 2.1 North-south trade and transit roads. |  |  |  |  |  |  |  |  |  |  |
|  | Nepal Army | - Kathmandu-Tarai-Madhesh Fast Track |  | 77 |  | 21 |  | Continue with opening track for remaining part – 55 km |  | Continue with curve & grade improvement, repair & maintenance and structure works including Bailey Bridge |  | Continue with curve & grade improvement, repair & maintenance and structure works including Bailey Bridge |
|  |  | - Banglung Beni Jomsom |  | 97 |  |  |  | Continue with curve & grade improvement, repair & maintenance and structure works |  | Continue with curve & grade improvement, repair & maintenance and structure works |  | Continue with curve & grade improvement, repair & maintenance and structure works |
|  | DoR DoR | - Kathmandu-Tarai-Madhesh Fast Track |  | 77 |  |  |  | Continue with Land acquisition and other activities |  | Continue with Land acquisition and other activities |  | Continue with Land acquisition and other activities |
|  |  | - Banglung Beni Jomsom |  | 97 |  | 97 |  | Continue with BT works - 2 km, GR works – 0.3 km |  | Continue with BT works - 3 km, GR works – 17 km |  | Continue with BT works - 4 km, GR works – 18 km |
|  |  | - Syaphrubesi Rasuwagadhi |  | 16 |  | 16 |  | Continue with GR works – 9 km, and Bridge -9 nos. |  | Continue with GR works – 7 km, and Bridge -9 nos. |  | Continue with Bridge -9 nos. |
|  |  | - B P Koirala Lokmarg (Banepa-Sindhuli-Bardibas) |  | 160 |  | 123 |  | Continue with BT works for 18 km Drain & structures in 4 km stretch of third section. |  | Continue with BT works for 10 km |  | Continue with BT works for 15 km |
|  |  | - Mahakali Lokjmarg (Darchula-Tinker Section) |  | 90 |  | 3 |  | Continue with opening track – 25 km Complete bridge design and EIA and contract to be awarded |  | Continue with opening track – 32 km |  | Continue with opening track – 30 km |
|  |  | - 4 NS trade & Transit Roads under RIP- 6 lane widening of 4 road sections namely (i) Rani Itahari-Dharan 50km (ii) Birgunj Pathlaiya 28km, (iii) Beliya-Butwal 24 km, (iv) Suryabinayak-Dhulikhel 16km. |  | 118 |  |  |  | Survey and DPR Preparation, Tendering & Contract Award plus Construction of Embankments. |  | Complete widening & strengthening of 4 roads - 20 km |  | Complete widening & strengthening of 4 roads - 45 km |
|  |  | - Sankhu Melamchi & Tokha-Chhahare under Road Improvement Project(RIP) |  | 58 |  |  |  | Continue with BT works for 28 km – (included under RIP in 1.2 as above) |  | Continue with BT works for remaining 21 km (included under RIP in 1.2 as above) |  |  |
|  |  | - 7 North-South Roads along Karnali, Kaligandaki & Koshi |  | 931 |  | 491 |  | Continue with track opening – 70 km and GR works – 5 km. Prepare DPR |  | Continue with track opening – 100 km and GR works – 30 km. |  | Continue with track opening – 110 km and GR works – 90 km. Start BT works – 5 km |
|  |  | 2. 2 Mid Hill Road Development Program |  |  |  |  |  |  |  |  |  |  |
|  | Nepal Army | - Musikot-Burtibang |  | 145 |  | 28 |  | Continue with track opening – 8 km |  | Continue with track opening – 6 km |  | Continue with track opening – 4 km |
|  | DoR DoR | - Puspalal Lokmarg (Mid Hill Lokmarg) |  | 810 |  | 584 |  | Continue with track opening – 226 km and GR works – 15 km |  | Continue with track opening – 15 km and GR works – 140 km |  | Continue with track opening – 20 km and GR works – 150 km |
|  |  | 2.3 Upgradation of Postal (Hulaki) and other roads of strategic importance |  |  |  |  |  |  |  |  |  |  |
|  |  | - Postal Roads including Bridges (Phase I only, Total three phase 1500km) |  | 640 |  |  |  | Continue with BT works – 33 km Continue with Bridges – 5 no. |  | Continue with BT works – 640 km Continue with Bridges – 16 no. |  | Continue with BT works – 430 km Continue with Bridges – 18 no. |
|  |  | - Rapti Lokmarg (Sallyan-Musikot Blacktop) |  | 86 |  |  |  | Continue with GR works – 30 km |  |  |  |  |
|  |  | - Kanti Lokpath |  | 93 |  |  |  | Continue with BT works – 1 km and GR works – 12 km |  | Continue with BT works – 1.5 km and GR works – 16 km |  | Continue with BT works – 2 km and GR works – 16 km |
|  |  | - Naradmuni Thulung Marg (Hile-Leguwaghat-Bhojpur) |  | 93 |  |  |  | Continue with GR works – 15 km |  | Continue with GR works – 12 km |  | Continue with GR works – 11 km |
|  |  | - Ganeshman Singh Marg(Thankot-Chitlang) |  | 20 |  |  |  | Continue with BT works – 1 km |  | Continue with BT works – 4 km |  | Continue with BT works – 2 km |
|  |  | - Byas Marg |  | 31 |  |  |  | Continue with BT works – 6 km |  | Continue with BT works – 5 km |  | Continue with BT works – 5 km |
|  |  | - Dharan Chatara Gaighat Katari Sindhuli Bazar-Hetauda |  | 325 |  |  |  | Continue with BT works – 8 km and GR works – 8 km |  | Continue with BT works – 13 km and GR works – 13 km |  | Continue with BT works – 17 km and GR works – 17 km |
|  |  | - 11 Kilo Chhepetar Bhaluswara Warpak |  | 53 |  |  |  | Continue with BT works – 3.2 km and GR works – 5 km |  | Continue with BT works – 4 km and GR works – 6 km |  | Continue with BT works – 4 km and GR works – 6 km |
|  |  | - Fikkal Shree Antu Danda Road |  | 14 |  |  |  | Continue with BT works – 3.5 km |  | Continue with BT works – 4 km |  | Continue with BT works – 4.5 km |
|  |  | - Dakchinkali Chaimale Sisneri Kulekhani |  | 19 |  |  |  | Continue with BT works – 8 km |  | Continue with BT works – 11 km |  |  |
|  |  | - Road Connectivity Project II (Pdirect.& Consultancy Services and road upgrading) |  | 300 |  |  |  | Selection of Consultant |  | Survey, Design and Contract Award |  | Commence BT works – 15 km |
|  |  | 2.4 New Road Construction and Extension |  |  |  |  |  |  |  |  |  |  |
|  |  | - Sagarmatha Lokmarg (Gaighat- Diktel Section) |  | 131 |  | 48 |  | Continue with track opening – 7 km, GR works –5 km and BT works –0.5 km |  | Continue with track opening – 15 km and GR works – 7 km |  | Continue with track opening – 25 km and GR works – 7 km |
|  |  | - Seti Lokmarg ( Tikapur-Lode-Chainpur-Taklakot) - Survey & EIA for 40 km to be done for each of three years |  | 285 |  | 22 |  | Continue with track opening – 9 km and GR works – 3 km |  | Continue with track opening – 15 km and GR works – 3 km |  | Continue with track opening – 19 km and GR works – 4 km |
|  |  | - Tourism Roads - 23 road sections for upgrading and new construction |  |  |  |  |  | Started this year 2067-68, Complete BT upgrading works - 10 km Start ER works –20 km |  | Continue with BT upgrading works - 10 km , ER works –5 km and GR works – 5 km |  | Continue with BT upgrading works - 15 km , ER works –5 km and GR works – 5 km |
|  |  | - Central Level (Various phase-wise roads) |  |  |  |  |  | Continue with track opening – 90 km, GR works – 20 km and BT works – 3 km |  | Continue with track opening – 90 km, GR works – 20 km and BT works – 3 km |  | Continue with track opening – 90 km, GR works – 20 km and BT works – 3 km |
|  |  | - Regional Level Roads (34 plus 40 Nos) |  | 0 |  |  |  | Continue with track Opening and ER roads – 70 km, GR works – 40 km |  | Continue with track Opening and ER roads – 70 km, GR works – 40 km and BT – 30 km |  | Continue with GR works – 70 km |
|  |  | - Gangate Labhdu Samudratar Galfu Bhanjyang |  | 63 |  | 35 |  | Continue with track opening – 5 km and BT works – 3 km |  | Continue with track opening – 6 km and BT works – 3 km |  | Continue with track opening – 8 km and BT works – 3 km |
|  |  | - Saljhundi Sandhikhark Dhorpatan Road |  | 128 |  | 62 |  | Continue with track opening – 14 km and GR works – 2 km |  | Continue with track opening – 30 km |  | Continue with track opening – 22 km and GR works – 5 km |
|  |  | - Chepang Marg (Bhandara-Lothar-Malekhu) |  | 60 |  | 50 |  | Continue with track opening – 10 km and GR works – 15 km |  | Continue with GR works – 28 km |  | Continue with GR works – 17 km |
|  |  | - Tanakpur Link Road |  | 14 |  | 14 |  | Continue with BT works – 6 km |  | Continue with BT works – 5 km |  | Continue with BT works – 3 km |
|  |  | - Sahid Marg (Tila Ghartigaon Thawang Rukumkot) - track to be opened upto MHH |  | 177 |  | 103 |  | Continue with track opening – 15 km |  | Continue with track opening – 15 km and GR works – 5 km |  | Continue with track opening – 20 km |
|  |  | - Benighat Aarughat Larkebhanjyang |  | 130 |  | 36 |  | Continue with track opening – 15 km |  | Continue with track opening – 6 km |  | Continue with track opening – 6 km |
|  |  | - Tallo Dhungeshore Satkhamba Dullu Pipalkot Dailekh |  | 33 |  | 29 |  | Continue with track opening – 3 km |  | Continue with track opening – 1 km and start GR works – 3 km |  | Continue with GR works – 5 km |
|  |  | - Gumi -Patihalna Chour (Surkhet) |  | 45 |  | 16 |  | Continue with track opening – 3 km |  | Continue with track opening – 3 km |  | Continue with track opening – 3 km |
|  |  | - Mirdi Kyakmi Bhimad |  | 59 |  | 52 |  | Continue with track opening – 3 km |  | Continue with track opening –2 km |  | Continue with track opening – 2 km |
|  |  | - Putalikhet-Karkineta-Kusma |  | 47 |  | 23 |  | Continue with track opening – 5 km |  | Continue with track opening – 10 km |  | Continue with track opening – 9 km |
|  |  | 2.5 Bridge Construction Program |  |  |  |  |  |  |  |  |  |  |
|  | DoR | - Bridge Construction along the Postal Roads |  |  |  |  |  | Refer section 2.3 above under Postal Roads |  |  |  |  |
|  |  | - Sunkoshi Bridge (Road Connectivity Project I) |  |  |  |  |  | Refer section 1.2 above under Road Connectivity Project |  |  |  |  |
|  |  | - Bridge Construction Program |  |  |  |  |  | Total 227 bridges under construction – 45 bridges to be completed this year |  | 50 bridges to be completed |  | 55 bridges to be completed |
|  | MoPPW | - Koshi Bridge (Chatara) (Flood Damaged Reconstruction Project) |  |  |  |  |  | Bridge construction at Chatra to continue |  | Bridge construction at Chatra to continue |  | Bridge construction at Chatra to continue |
| - Programs for expansion and improvement of transport facilities in the Kathmandu Valley and other urban centers of the country. | DoR | - Kathmandu Bhaktapur Road Extension |  | 9 |  |  |  | 1.7 km of remaining BT on main lanes to be completed and BT works on service roads & other auxiliary works to continue |  | other auxiliary works to continue and completed |  |  |
|  |  | - Kathmandu Valley Road Construction and Improvement |  | salbasali |  |  |  | Continue with BT works – 55 km. on different road sections in the valley |  | Continue with BT works – 60 km. on different road sections in the valley |  | Continue with BT works – 65 km. on different road sections in the valley |
|  |  | - Kathmandu Valley Road Extension Project |  | salbasali |  |  |  | Continue with BT works – 20 km. & widening strengthening 6 km |  | Continue with BT works – 35 km. & widening strengthening 10 km |  | Continue with BT works – 35 km. & widening strengthening 10 km |
|  |  | - Other Urban Roads |  | salbasali |  |  |  | Continue with BT works – 10 km. & earthen works 10 km |  | Continue with BT works – 10 km. & Gravel 10 km |  | Continue with BT works – 10 km. & Gravel 15 km |
|  | MoPPW and PIU-DoR | - Kathmandu Sustainable Urban Transport Project |  |  |  |  |  | - Project Management and Capacity Building – selection of consultants. - Preparation for construction of bus stop, lay-bys, shelters, bus lanes, terminals and road junction improvement. |  | - Technical studies Public Advocacy-awareness, Training and Capacity Building of PMCO, PMIU-MOEnv, DoR, KMC, DOTM & MTPD - Civil Works Contract for Bus stops, lay-bys, shelters and improvement to Lekhanath / Lazimpat Junction, and works from, Teku to Sorhakhutte Pati - Procurement of Traffic Signals |  | - Continue & complete technical studies Public Advocacy-awareness, training and Capacity Building of PMCO, PMIU-MOEnv, DoR, KMC, DOTM & MTPD - Construction of Bus stops, lay-bys, shelters and improvement to Lekhanath / Lazimpat Junction, and works from, Teku to Sorhakhutte Pati - Installation of Traffic Signals |
| - Programs for Feasibility studies and R&D on alternative transport (railways, waterways, ropeways etc.) system as well as on road safety. | DoR | - Detailed Feasibility Studies of Roads and Bridges |  |  |  |  |  |  |  |  |  |  |
|  |  | - Planning, Program, M&E, Geo-environment studies etc. |  |  |  |  |  |  |  |  |  |  |
|  |  | - Transport Project Preparatory Facilitation (Feasibility & Design ADB) |  |  |  |  |  |  |  |  |  |  |
| - Program for Road Strengthening and Repair Maintenance | DoR | - Karnali Lokmarg (Surkhet- Jumla) |  | 232 |  |  |  | Out of 232km, 126 km under RSDP for upgrading, rest between Kalikot-Jumla 106km track for curve & grade improvement |  |  |  |  |
|  |  | - Jaya Prithvi Bhadur Singh Marga, Khodpe bajhhang |  | 110 |  |  |  | Out of 65km track, 45 km under RSDP for upgrading and curve & grade improvement, repair & maintenance for rest of track. |  |  |  |  |
|  |  | - Damak Chisapani |  | 44 |  |  |  | 3 km GR in 2067-68 and 4km GR for next 2 years plus Grade & curve improvements, const. of Structures, repair & maintenance |  |  |  |  |
|  |  | - Bridge-culvert Conservation and Maintenance & Repair |  |  |  |  |  | 9 bridge in SRN to be repaired, historical data on SRN & FR bridges to be collected |  |  |  |  |
|  | MoPPW | - Flood Damaged Reconstruction Project |  |  |  |  |  | Repair & maintenance |  | Repair & maintenance |  | Repair & maintenance |
|  | RBN | - Road Boards Strategic Roads Periodic Maintenance |  | 1950 |  |  |  | Periodic Maintenance -400 km |  | Periodic Maintenance -700 km |  | Periodic Maintenance -800 km |
|  |  | - Road Boards Routine, Recurrent and Emergency Maintenance |  |  |  |  |  |  |  |  |  |  |
|  | Nepal Army | - Chhinchu Jajarkot |  |  |  |  |  | Grade & curve improvements, repair & maintenance for part of 45 km track that was opened under RSDP |  |  |  |  |
|  |  | - Devasthal-KanaiDanda-Chaurjhari |  |  |  |  |  | Grade & curve improvements, repair & maintenance for entire stretch |  |  |  |  |
| - Programs for Institutional Strengthening - including M&E and recurrent administrative budget expenses | DoR | Miscellaneous |  |  |  |  |  |  |  |  |  |  |
|  |  | - Machinery Repair & Maintenance |  |  |  |  |  |  |  |  |  |  |
|  |  | - Purchase of mechanical equipments |  |  |  |  |  |  |  |  |  |  |
|  |  | - Road Transport Security, Control of Encroachment and Border Security |  |  |  |  |  |  |  |  |  |  |

VII. Budget Allocation

The budget allocation for the core business activities are presented in Table 4.

Table 4: Budget Allocation for Core Business Activities: DoR, FY 2010/11-20012/13

(Amount in Rs '000)

| Major Programs |  | Core Business Activities/ Projects | Budget Heading | FY 2009/10 Allocated |  |  |  | FY 2010/11 Allocated |  |  | Total for FY 2010/11-2012/13 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Recrt. | Capital | Total |  | Recrt. | Capital | Total | Recrt. | Capital | Total |
| 1. Program for connecting DHQs. i. New Road Construction and, ii. Road Upgradation | Nepal Army | Nagma-Gamgadhi | 48-4-404 |  | 170,000 | 170,000 |  |  | 87,400 | 87,400 | - | 284,200 | 284,200 |
|  |  | Jajarkot-Dunai(Dolpa) | 48-4-405 |  | 80,000 | 80,000 |  |  | 85,500 | 85,500 | - | 282,300 | 282,300 |
|  |  | Besisahar Chame -NA | 48-4-579 |  | 185,700 | 185,700 |  |  | 80,000 | 80,000 | - | 185,000 | 185,000 |
|  | DoR | North South Lok Marg (Karnali: Hilsa - Simikot Section) | Refer 48-4-248 (411) below |  |  | - |  |  |  |  |  |  |  |
|  | DoR | Road Improvement Project(RIP) - (total 17 nos.) including 8 road sections connecting DHQ | 48–3÷4–394 | 14,628 | 1,334,594 | 1,349,222 |  | 21,427 | 2,492,386 | 2,513,813 | 65,346 | 6,443,986 | 6,509,332 |
|  |  | Road Sector Development Project I & II -(total) including 5 roads connecting DHQ and periodic maintenance works | 48–3/4–407 | 12,568 | 1,143,549 | 1,156,117 |  | 15,981 | 2,246,740 | 2,262,721 | 43,563 | 8,608,522 | 8,652,085 |
|  |  | Sub-regional Transport Enhancement Project including 4 roads connecting DHQs | 48–3÷4–548 |  |  | - |  | 5,963 | 823,959 | 829,922 | 24,720 | 5,497,005 | 5,521,725 |
|  |  | 5 roads under Road Connectivity Project I + Sunkoshi Bridge | 48–3÷4–559 | 16,766 | 1,558,939 | 1,575,705 |  | 22,874 | 2,763,708 | 2,786,582 |  |  | 4,073,110 |
| 2. Programs for improving accessibility in dense settlements of terai and hills as well as administrative, commercial, tourism and industrial centers. |  | 2.1 North-south trade and transit roads. |  |  |  |  |  |  |  |  |  |  |  |
|  | Nepal Army | - Kathmandu-Tarai-Madhesh Fast Track |  |  |  | - |  |  | 150,000 |  | - | 450,000 |  |
|  |  | - Banglung Beni Jomsom |  |  |  | - |  |  | 28,000 | 28,000 | - | 28,000 | 28,000 |
|  | DoR | - Kathmandu-Tarai-Madhesh Fast Track | 48–3÷4–406 | 2,167 | 245,031 | 247,198 |  | 4,594 | 678,063 | 682,657 | 14,377 | 3,928,713 | 3,943,090 |
|  |  | - Banglung Beni Jomsom | 48–4–270 |  | 44,146 | 44,146 |  |  | 10,000 | 10,000 | - | 125,500 | 125,500 |
|  |  | - Syaphrubesi Rasuwagadhi | 48–3÷4–375 | 1,491 | 385,495 | 386,986 |  | 2,016 | 632,750 | 634,766 |  |  | 644,766 |
|  |  | - B P Koirala Lokmarg (Banepa-Sindhuli-Bardibas) | 48–3÷4–202 | 5,242 | 273,131 | 278,373 |  | 5,605 | 718,440 | 724,045 | 16,911 | 3,768,840 | 3,785,751 |
|  |  | - Mahakali Lokjmarg (Darchula-Tinker Section) | 48–3÷4–205 |  | 180,000 | 180,000 |  | 4,353 | 189,050 | 193,403 | 13,176 | 739,050 | 752,226 |
|  |  | - 4 NS trade & Transit Roads under RIP (6 lane widening of 4 road sections namely (i) Rani Itahari-Dharan 50km (ii) Birgunj Pathlaiya 28km, (iii) Beliya-Butwal 24 km, (iv) Suryabinayak-Dhulikhel 16km. | Refer 48–3÷4–394 as above | Budget included in I-2 under RIP as above |  |  |  |  |  |  |  |  |  |
|  |  | - Sankhu Melamchi & Tokha-Chhahare under Road Improvement Project(RIP) |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - 7 North-South Roads along Karnali, Kaligandaki & Koshi | 48-4-411 | 6,059 | 305,394 |  | 311,453 | 11,670 | 532,000 | 543,670 | 35,368 | 2,322,000 | 2,357,368 |
|  |  | 2. 2 Mid Hill Road Development Program |  |  |  |  |  |  |  |  |  |  |  |
|  | Nepal Army | Musikot-Burtibang | 48–4–386 |  | 42,000 |  | 42,000 |  | 38,500 | 38,500 | - | 78,500 | 78,500 |
|  | DoR | Puspalal Lokmarg (Mid Hill Lokmarg) | 48–3÷4–403 | 5,974 | 1,250,302 |  | 1,256,276 | 7,269 | 1,202,000 | 1,209,269 | 22,006 | 4,804,000 | 4,826,006 |
|  |  | 2.3 Upgradation of Postal (Hulaki) and other roads of strategic importance |  |  |  |  |  |  |  |  |  |  |  |
|  | DoR | - Postal Roads including Bridges (Phase I only, Total three phase 1500km) | 48–3÷4–294 | 1,861 | 743,921 |  | 745,782 | 3,976 | 2,810,000 | 2,813,976 | 11,591 | 17,112,385 | 17,123,976 |
|  |  | - Rapti Lokmarg (Sallyan-Musikot Blacktop) | 48–3÷4–203 |  | 56,700 |  | 56,700 |  | 28,500 | 28,500 | - | 28,500 | 28,500 |
|  |  | - Kanti Lokpath | 48–4–206 | 1,890 | 46,687 |  | 48,577 | 2,310 | 50,000 | 52,310 | 7,145 | 170,000 | 177,145 |
|  |  | - Naradmuni Thulung Marg (Hile-Leguwaghat-Bhojpur) | 48–3÷4–255 | 3,052 | 45,887 |  | 48,939 | 3,575 | 19,000 | 22,575 | 10,974 | 59,000 | 69,974 |
|  |  | - Ganeshman Singh Marg(Thankot-Chitlang) | 48–4–264 |  | 4,924 |  | 4,924 |  | 10,000 | 10,000 | - | 70,000 | 70,000 |
|  |  | - Byas Marg | 48–4–296 |  | 39,953 |  | 39,953 |  | 50,000 | 50,000 | - | 130,000 | 130,000 |
|  |  | - Dharan Chatara Gaighat Katari Sindhuli Bazar-Hetauda | 48–4–315 | 2,495 | 62,244 |  | 64,739 | 3,185 | 100,000 | 103,185 | 9,787 | 470,000 | 479,787 |
|  |  | - 11 Kilo Chhepetar Bhaluswara Warpak | 48–3÷4–401 | 3,131 | 45,969 |  | 49,100 | 3,482 | 48,000 | 51,482 | 11,493 | 163,000 | 174,493 |
|  |  | - Fikkal Shree Antu Danda Road | 48–4–409 |  | 22,209 |  | 22,209 |  | 25,000 | 25,000 | - | 85,000 | 85,000 |
|  |  | - Dakchinkali Chaimale Sisneri Kulekhani | 48-4-587 |  |  |  |  |  | 32,775 | 32,775 | - | 142,775 | 142,775 |
|  |  | - Road Connectivity Project II (Pdirect.& Consultancy Services and road upgrading) |  |  |  |  |  |  |  |  |  |  | 3,375,000 |
|  |  | 2.4 New Road Construction and Extension |  |  |  |  |  |  |  |  |  |  |  |
|  | DoR | - Sagarmatha Lokmarg (Gaighat- Diktel Section) | 48–3÷4–201 | 1,550 | 40,966 |  | 42,516 | 3,005 | 63,621 | 66,626 | 9,057 | 237,491 | 246,548 |
|  |  | - Seti Lokmarg ( Tikapur-Lode-Chainpur-Taklakot) - Survey & EIA for 40 km to be done for each of three years | 48–4–208 |  | 19,999 |  | 19,999 |  | 80,000 | 80,000 | - | 260,000 | 260,000 |
|  |  | - Tourism Roads - 23 road sections for upgrading and new construction | 48-4-248 |  |  |  |  |  | 110,000 | 110,000 |  | 360,000 | 360,000 |
|  |  | - Central Level (Various phase-wise roads) | 48–4–249 |  | 808,892 |  | 808,892 |  | 1,150,000 | 1,150,000 | - | 3,350,000 | 3,350,000 |
|  |  | - Regional Level Roads (34 plus 40 Nos) | 48–3÷4–297 |  | 287,310 |  | 287,310 |  | 600,000 | 600,000 | - | 1,850,000 | 1,850,000 |
|  |  | - Gangate Labhdu Samudratar Galfu Bhanjyang | 48–4–282 |  | 42,935 |  | 42,935 |  | 40,000 | 40,000 | - | 132,400 | 132,400 |
|  |  | - Saljhundi Sandhikhark Dhorpatan Road | 48–3÷4–285 |  | 42,190 |  | 42,190 | 3,150 | 38,000 | 41,150 | 9,590 | 218,000 | 227,590 |
|  |  | - Chepang Marg (Bhandara-Lothar-Malekhu) | 48–3÷4–286 |  | 14,602 |  | 14,602 |  | 76,000 | 76,000 | - | 236,000 | 236,000 |
|  |  | - Tanakpur Link Road | 48–4–376 |  |  |  | - |  | 54,500 | 54,500 | - | 165,730 | 165,730 |
|  |  | - Sahid Marg (Tila Ghartigaon Thawang Rukumkot) - track to be opened upto MHH | 48–3÷4–402 | 3,015 | 89,793 |  | 92,808 | 3,322 | 97,850 | 101,172 | 10,140 | 331,092 | 341,232 |
|  |  | - Benighat Aarughat Larkebhanjyang | 48–3÷4–415 | 681 | 29,828 |  | 30,509 |  | 28,500 | 28,500 | - | 88,500 | 88,500 |
|  |  | - Tallo Dhungeshore Satkhamba Dullu Pipalkot Dailekh | 48–4–358 |  | 8,790 |  | 8,790 |  | 15,000 | 15,000 | - | 39,255 | 39,255 |
|  |  | - Gumi -Patihalna Chour (Surkhet) | 48–4–368 |  | 8,375 |  | 8,375 |  | 10,000 | 10,000 | - | 34,255 | 34,255 |
|  |  | - Mirdi Kyakmi Bhimad | 48–4–399 |  | 9,111 |  | 9,111 |  | 12,000 | 12,000 | - | 35,100 | 35,100 |
|  |  | - Putalikhet-Karkineta-Kusma | 48–4–400 |  | 13,220 |  | 13,220 |  | 15,000 | 15,000 | - | 61,200 | 61,200 |
|  |  | 2.5 Bridge Construction Program |  |  |  |  |  |  |  |  |  |  |  |
|  | DoR | - Bridge Construction along the Postal Roads | 48–3÷4–294 |  |  |  | - |  |  | - | - | - | - |
|  |  | - Sunkoshi Bridge (Road Connectivity Project I) | 48–3÷4–559 | see above |  |  |  |  |  | - | - | - | - |
|  |  | - Bridge Construction Program | 48–4–650 |  | 2,252,257 |  | 2,252,257 |  | 1,900,000 | 1,900,000 | - | 6,400,000 | 6,400,000 |
|  |  | - Koshi Bridge (Chatara) (Flood Damaged Reconstruction Project) | 48–4–682 | 90,197 | 482,401 |  | 572,598 | 160,139 | 429,273 | 589,412 | 177,467 | 1,214,113 | 1,391,580 |
| 3. Programs for expansion and improvement of transport facilities in the Kathmandu Valley and other urban centers of the country . | DoR | - Kathmandu Bhaktapur Road Extension | 48–3÷4–408 | 2,332 | 840,600 |  | 842,932 | 3,131 | 905,465 | 908,596 | 6,262 | 955,465 | 961,727 |
|  |  | - Kathmandu Valley Road Construction and Improvement | 48–4–500 |  | 260,480 |  | 260,480 |  | 250,000 | 250,000 | - | 820,000 | 820,000 |
|  |  | - Kathmandu Valley Road Extension Project | 48–3÷4–503 | 4,201 | 203,852 |  | 208,053 | 4,854 | 237,500 | 242,354 | 15,337 | 937,500 | 952,837 |
|  |  | - Other Urban Roads | 48–4–502 |  | 94,933 |  | 94,933 |  | 160,000 | 160,000 | - | 426,500 | 426,500 |
| 4. Programs for Feasibility studies and R&D on alternative transport (railways, waterways, ropeways etc.) system as well as on road safety. | DoR | - Detailed Feasibility Studies of Roads and Bridges | 48–4–661 |  | 148,634 |  | 148,634 |  | 28,500 | 28,500 | - | 78,500 | 78,500 |
|  |  | - Planning, Program, M & E, Geo-environment studies etc. | 48–4–681 |  | 23,538 |  | 23,538 | 16,005 | 19,000 | 35,005 | 49,505 | 134,000 | 183,505 |
|  |  | - Transport Project Preparatory Facilitation (Feasibility & Design ADB) |  |  |  |  |  |  |  |  |  |  | 292,000 |
| 5. Program for Road Strengthening and Repair Maintenance | DoR | - Karnali Lokmarg (Surkhet- Jumla) | 48–3÷4–204 | 3,143 | 37,871 |  | 41,014 | 3,669 | 29,731 | 33,400 | 11,419 | 29,731 | 41,150 |
|  |  | - Jaya Prithvi Bhadur Singh Marga, Khodpe bajhhang | 48–3÷4–275 |  | 6,428 |  | 6,428 |  | 10,000 | 10,000 | - | 10,000 | 10,000 |
|  |  | - Damak Chisapani | 48–4–302 |  | 25,302 |  | 25,302 |  | 15,000 | 15,000 | - | 39,600 | 39,600 |
|  |  | - Bridge-culvert Conservation and Maintenance & Repair | 48–4–660 |  | 49,335 |  | 49,335 |  | 308,750 | 308,750 | - | 1,958,750 | 1,958,750 |
|  | MoPPW | - Flood Damaged Reconstruction Project | 48–4–682 | 90,197 |  |  | 90,197 |  |  |  |  |  |  |
|  | RBN | - Road Boards Strategic Roads Periodic Maintenance |  | 14,500 | 1,300,000 |  | 1,314,500 | 18,000 | 2,500,000 | 2,518,000 | 54,000 | 9,000,000 | 9,054,000 |
|  |  | - Road Boards Routine, Recurrent and Emergency Maintenance | 48–3÷4–695 |  |  |  | - |  |  | 642,600 | - | - | 2,313,360 |
|  | Nepal Army | - Chhinchu Jajarkot | 48–3÷4–272 | 816 | 35,105 |  | 35,921 |  | 20,000 | 20,000 | - | 20,000 | 20,000 |
|  |  | - Devasthal-KanaiDanda-Chaurjhari | 48–4–364 |  | 20,000 |  | 20,000 |  | 15,000 | 15,000 | - | 70,000 | 70,000 |
| 6. Programs for Institutional Strengthening - include M&E and recurrent administrative budget expenses | DoR | Miscellaneous |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - Compensation | 48–4–664 | 29,824 | 29,824 |  |  | 30,000 | 30,000 | - | 300,000 | 300,000 | 29,824 |
|  |  | - Machinery Repair & Maintenance | 48–4–670 | 39,982 | 39,982 |  |  | 38,000 | 38,000 | - | 128,000 | 128,000 | 39,982 |
|  |  | - Purchase of mechanical equipments | 48–4–671 | 11,947 | 11,947 |  |  | 61,800 | 61,800 | - | 149,800 | 149,800 | 11,947 |
|  |  | - Road Transport Security, Control of Encroachment and Border Security | 48–4–673 | 9,111 | 9,111 |  |  | 14,250 | 14,250 | - | 104,250 | 104,250 | 9,111 |
|  | RBN |  |  |  |  |  |  |  |  |  |  |  |  |

### Institutional Development

  - Improvement in Implementation System

- The proposals for improvement in implementation system are as follows:

- The required human and other resources will be mobilized for the management and execution of programs.

- Appropriate measures will be undertaken to avoid re-occurrence of problems that were encountered during the implementation of programs in the past.

- With the purpose of improving the implementation aspects, requisite training, seminar and workshops will continue to be organized for enhancing the capacity of the existing human resources. Besides, required manuals will continue to develop.

- Highway Management Information System (HMIS) will continue to strengthen at all levels.

- Implementation Plans will be prepared for timely completion of projects and the resources will be mobilized accordingly.

- The management infrastructure will continue to improve with result focus.

- Contractual arrangements will continue to be made for the necessary period in such a way that prioritized projects are completed within the assigned period and the annually disbursed budgets. The contracts shall be awarded within the first quarter.

- In order to institutionalize the quality control system of construction works, the testing and regular monitoring system will continue to be developed as per the approved Quality Assurance Plan.

- The internal elements that help create negative influence towards project implementation will be identified and mitigated. Appropriate measures will be undertaken to mitigate the negative impacts of external elements as well.

- Technical Auditing will continue to develop as an integral component of the project execution implementation.

- Monitoring and Evaluation

- The major proposals for improved monitoring and evaluation of DoR are as follows:

- The project will be regularly monitored at different levels and the feedback so received will be used for improving the projects.

- Required resources will be mobilized for developing the Regional Road Directorate as the permanent monitoring entity.

- Technical Auditing will be undertaken for some of the projects so as to monitor the implementation status at each stage of project execution.

- The economic and physical indicators related to impact and progress of the projects as well as their source of information will be defined to facilitate effective monitoring and evaluation.

- In addition to monitoring of the physical progress, arrangements will be made to gradually adopt the implementation process monitoring as well.

- On-site monitoring on a quarterly basis will be done for large projects of national importance.

- Arrangements will be made for monitoring the district level projects through the local bodies.

- The system of fund disbursement will be adopted in such a way that fund for the preceding quarter is released based on performance in the preceding quarter.

- Arrangements will be made for regular Independent and Public Auditing of the projects.

- Collection of base line data before the commencement of projects will be highly emphasized and Post Evaluation/ Impact Assessment will be done after the completion of projects. The lessons learnt will be used for the formulation of future projects.

- Recently, with the objective to ensure accomplishment of adopted plans, policies, programs and projects within the prescribed time, quantity, quality standards and investments, the National Planning Commission has issued the Results Based Monitoring and Evaluation Guideline 2067 as a means to enable regular, dependable, and effective monitoring and evaluation functions. The guideline is also an attempt to assure the stakeholders and development partners of the optimal utilization of public expenditure towards realization of results oriented plans, policies and programs (see Annex II).

- Following the recommended framework of the NPC Guideline 2067, a Results Based Monitoring Framework for implementing the programs and activities as proposed in the business plan of DoR has been contextualized and produced in Appendix II-2 for outcome monitoring, Appendix II-3 for output monitoring, and Appendix II-4 for budget monitoring. The design of the monitoring frameworks is derived from the Results Frameworks for DoR (ref. Annex I) for outcome monitoring (Appendix II-2). Similarly, for monitoring of outputs (Appendix II-3) and of budget (Appendix II-4), Table 2 and 4 of the Business Plan are referred to. In the absence of baseline information for the goal and objectives, the impact monitoring is deferred to for the later stages of MfDR implementation.

The proposed Results Based Monitoring Framework (ref. Appendix II-2, II-3 and II-4) has been put to use and tested recently during an interaction program participated by the concerned officials.

### Critical Factors for Successful Implementation

- In order to achieve the TYP targets through the effective implementation of the business plan, a number of challenges will need to be addressed:

- As noted in paragraph 9 above, there is a need to ensure that all the stakeholders have a clear and common understanding of the Government’s policy and strategy shifts in the sector. This will assist in implementation of the policy and strategy as unproductive debates will be avoided and, more importantly, the processing of legal documents/agreements, for example, would be smoother and quicker.  Thus, effective communication campaigns on what the reforms are, why are they needed etc. should be carried out to make all stakeholders aware of the policy/strategy shifts and the need to implement them.

- To meet the TYP targets there is a need to scale up service delivery. Further, the different modalities for channelling of funds currently in place should be recognized. It should be understood that through effective sector monitoring over the TYP period, the Government would have a strong basis to decide the suitability and preparedness of the sector to adopt a sector wide approach.

- Ensuring effective implementation of programs and activities in the present environment of conflict is another challenge. It is, no doubt, essential to ensure faster implementation and better outcomes to bring visible progress to conflict-affected areas, as well as others.

- Finally, instituting and making operational an effective Sector Monitoring and Evaluation System is another challenge.  So far, the efforts are on the right direction, however, there is a need for the Government to take full ownership and demonstrate action oriented commitment to this important activity. An effective and credible M&E will not only assist the Government in ensuring the best value for money, as well as donor harmonization. Therefore, it is of utmost urgency that the sector M&E be implemented with full commitment on a war footing.

SRN includes the main highway and feeder roads,

For comparison with other countries, China currently invests about 4 to 5% of its GDP on expa7nding and maintaining its transport system, while Korea, during its development stage, used to spend about 5.2% of its GDP. Brazil spends about 2.4% of its GDP, and Bangladesh spends about 2.5% of its GDP. Most OECD countries, with mature transport network, invest about 3% of their GDP on maintaining their transport assets.

- Road building group

** Community based organization